Request for Proposal for Empanelment of Agencies for Supply, Installation, Commissioning, Training, Operation and Maintenance of Artificial Intelligence labs at Govt. ITIs and other Institutions across Chhattisgarh

System Tender No:

Chhattisgarh Infotech Promotion Society

Chief Executive Officer

Chhattisgarh Infotech Promotion Society State Data Center,

Civil Lines Raipur, (C.G.) 492001 E-mail: ceochips@nic.in

Website: https://www.chips.gov.in

CHiPS intends to empanel multiple agencies for Supply, Installation, Commissioning, Training, Operation and Maintenance of AI Labs in Government ITIs and other institutions across Chhattisgarh.

Bidders fulfilling the prescribed eligibility criteria of the RFP can access and download the complete RFP Document and other details from

The major events under the bid process are:

| Sr. No. | List of Key Events | Critical Dates |
| --- | --- | --- |
| 1 | Date of Issue of RFP | XX.XX.2026 |
| 2 | Date of submission of Pre-Bid Queries | XX.XX.2026 |
| 3 | Date of Pre-Bid Meeting | XX.XX.2026 |
| 4 | Date of publication of Pre-Bid Responses | XX.XX.2026 |
| 5 | Due Date for Submission of Proposal | XX.XX.2026 |
| 6 | Date of Opening of Technical proposal | To be communicated later |
| 7 | Date of Technical presentation | To be communicated to the technically qualified bidders |
| 8 | Date of Opening Financial Proposal | Through the e-tender portal to be intimated later by e-mail to the technically qualified bidders. |
| 9 | Method of Selection | Least Cost Selection (LCS) |

The proposals complete in all respect must be applied through e-tender process latest by XX.XX.2026 before XX:XX PM) clearly mentioning ‘Request for Proposal for Empanelment of Agencies for Supply, Installation, Commissioning, Training, Operation and Maintenance of Artificial Intelligence labs at Govt. ITIs and other Institutions across Chhattisgarh’’. The proposals received beyond the last date and time will be rejected without assigning any reason. The authority reserves all the rights to reject any/ all proposals at any stage without assigning any reason thereof

## DISCLAIMER

The information contained in this Tender Document provided to the Bidders, by the Chhattisgarh Infotech Promotion Society, Raipur, hereinafter referred to as CHiPS, or any of their employees or advisors, is provided to the Bidder(s) on the terms and conditions set out in this tender document and all other terms and conditions subject to which such information is provided.

The purpose of this tender document is to provide the Bidder(s) with information to assist in the formulation of Proposals. This tender document does not aim to hold all the information each Bidder may require. This tender document may not be appropriate for all persons, and it is not possible for the Chhattisgarh Infotech Promotion Society, their employees or advisors to consider the business/investment objectives, financial situation and particular needs of each Bidder who reads or uses this tender document. Each Bidder should conduct its own investigations and analysis and should check the accuracy, reliability and completeness of the information in this tender document and where it is necessary to obtain independent advice from appropriate sources.

Chhattisgarh Infotech Promotion Society, their employees and advisors make no representation or warranty and shall incur no liability under any law, statute, rules or regulations as to the accuracy, reliability or completeness of the tender document. Chhattisgarh Infotech Promotion Society may, in its absolute discretion, but without being under any obligation to do so, update, amend or supplement the information in this tender document

## FACT SHEET

| Sl. No. | Particular | Details |
| --- | --- | --- |
| 1. | Name of the Client | Chhattisgarh Infotech Promotion Society |
| 2. | Method of Selection | L1-Least Cost Selection (LCS) |
| 3. | Mode of Submission | https://eproc.cgstate.gov.in or https://www.chips.gov.in Three parts through e-Procurement Portal: Envelope A & B (scanned documents) online, Envelope C (Financial Bid) online only |
| 4. | Date of Issue of RFP(e-tender) | XX.XX.2026 |
| 5. | Deadline for Submission of Pre-Proposal Query | XX.XX.2026 |
| 6. | Date of Pre-Proposal Meeting | XX.XX.2026 |
| 7. | Due date for submission of proposals | XX.XX.2026 |
| 8. | Date of opening of Technical Proposal |  |
| 9. | Date of Technical Presentation and | To be informed to the technically qualified bidders later. |
| 10. | Date of Opening of Financial Proposal | Through the e-tender portal to be intimated later by e-mail to the technically qualified bidders |
| 11. | Bid Processing Fee (Non-Refundable) | Rs. 10,000/- to be paid online on eProcurement portal). |
| 12. | Earnest Money Deposit (EMD) (Refundable) | Rs. 5,00,000/- to be paid online on eProcurement portal |
| 13. | Performance Security | The Empaneled agencies shall furnish 10% of the Contract value in shape of Bank Guarantee/e-Bank Guarantee |
| 14. | Address of the Client: | Chief Executive Officer Chhattisgarh Infotech Promotion Society State Data Center, Civil Lines Raipur, (C.G.) 492001 E-mail: ceochips@nic.in Website: https://www.chips.gov.in |

Executive Summary

This RFP outlines the establishment of around 25 AI (Artificial Intelligence) and Data Labs in Industrial Training Institutes (ITIs/ Polytechnics /other institutions) across Chhattisgarh State, supplementing the India AI Mission's national initiative. The labs will serve as skill development centers for data annotation and AI applications, preparing students for careers in India's emerging AI ecosystem.

Key Objectives

- Establish state-of-the-art AI Data Labs across ITI and other institutions

- Train 180 students per lab for 3 years in data-intensive AI roles

- Bridge the gap between traditional vocational training and modern AI skills

- Create industry-ready workforce for data annotation and AI-related domains

- Support India's vision of AI for inclusive development

Expected Outcomes

- Trained workforce in Data Annotation and Data Curator (120-hour certified programs)

- State-level employment in data-intensive sectors

- Certification and pathways to higher education

- Foundation for advanced AI skilling

1. Background & Rationale

1.1 National Context: India AI Mission

India AI Mission, launched by the Ministry of Electronics and Information Technology (MeitY), aims to:

- Build a national AI compute infrastructure

- Expand AI/Data labs across institutions to boost AI research and skills.

- Promote a major AI skilling program to develop talent,

- The mission emphasizes affordable, democratized access to AI compute and resources

1.2 State-Level Opportunity

Leveraging the India AI Mission framework, the state proposes to:

- Complement central funding with state resources

- Ensure localized implementation and sustainability

- Build institutional capacity for long-term AI skilling

- Create sustainable employment pathways

- Develop state-specific AI applications and research

1.3 Target Institutions

Primary Beneficiaries:  ITI and Polytechnic institutions

Geographic Distribution: Mix of urban and semi-urban centers

Selection Criteria:

- Existing physical infrastructure

- Readiness and capacity for training delivery

- Student demand and employment ecosystem

- Proximity to industry clusters

- Adequate space and accessibility for students

2. Expected Outcomes & Impact

2.1 Student impact (3-year)

- Beneficiaries: Training of 180 students per lab over three years under NSQF-aligned AI and data courses.

- Courses completed: Students complete 120-hour Data Annotator Assistant and Data Curator Assistant courses or any other foundational AI/data modules as per directives of CHiPS

- Learning outcomes: Learners gain practical skills in Python, AI foundations, data annotation, data curation, data quality, and visualization through structured curricula and industry-linked practical projects.

- Career readiness: Continuous assessment and “Practical Projects with Industry” strengthen readiness for entry-level roles in data annotation, data curation, and related AI-support functions.

- Job Fair: Students completing 120-hour Data Annotator Assistant and Data Curator Assistant courses or any other foundational AI/data modules will be participating the state Level Job Fairs, Rojgaar Mela etc. and will get consumed in local IT companies and Emerging Startups.

### 3. Proposal Validity:

Proposal shall remain valid for a period of 180 (One Hundred Eighty) days from the date of opening of the technical proposal. The Client reserves the right to reject a proposal valid for a shorter period as non-responsive and will make the best efforts to finalize the selection process and award of the contract within the bid validity period. The bid validity period may be extended on mutual consent. If agreed upon, the bid security so deposited shall also be suitably extended.

### 4. Pre- Proposal Queries and Meeting:

The Bidder may request a clarification of any part of the RFP prior to the last date for submission of queries through email, as indicated in the Bidder’s Data Sheet. Bidders are allowed to submit their queries in respect of the RFP and other details if any, to CHiPS in the following format.

| S. No. | Section/Page No and RFP Clause reference. | Content of RFP requiring clarifications | Queries/ Change/Clarification requested |
| --- | --- | --- | --- |

A Pre-Bid meeting will be organized by CHiPS to address the queries relating to the overall selection process and scope of the work through Hybrid Mode (both virtual & physical mode) as per the timeline mentioned in the Data Sheet. The client will address the queries submitted by the bidders.

- The purpose of Pre-Bid discussion is to provide the Bidders with information regarding the RFP, project requirements, and opportunity to seek clarification regarding any aspect of the RFP and the project. However, CHiPS, reserves the right to hold or to reschedule the Pre-Bid meeting.

- CHiPS shall not be responsible for ensuring that the Bidder’s queries have been received by them. Any requests for clarifications received after Pre-Bid meeting will not be entertained.

- However, CHiPS makes no representation or warranty as to the completeness or accuracy of any response made in good faith, nor does it undertake to answer all the queries that have been submitted by the Bidders

- The Client's responses to Bidder queries will be made available to all Bidders and shall be uploaded on the Client’s website. It shall be the Bidder's responsibility to check the Client's website for the responses to the queries or requests for clarification.

- Any such corrigendum shall be deemed to be incorporated into this RFP and binding on all Bidders.

### 5. Submission of Proposals:

The bid should be submitted through online mode only in eProcurement Portal. The tender is to be submitted electronically in three separate Envelopes as indicated below:

### Envelope-A (Pre-Qualification Criteria Documents)

The bidder must furnish the documents as per Pre-Qualification Criteria duly signed in along with the Form 1 to Form-7.

### Envelope-B (Technical-Qualification Criteria Documents)

The bidder must furnish the documents as per Technical Qualification Criteria duly signed in along with their Technical Proposal.

### Envelope-C (Financial Bid)

The Price Bid (BoQ Ms-Excel format) only in eProcurement Portal

The offer must be submitted only though uploading in the eProcurement Portal, before the last date & time for bid submission.

Tender document (s) and all enclosures must contain the signature of the competent authority of the firm.

Pre-Qualification/Eligibility Criteria:

Before opening and evaluation of the technical proposals, each bidder will be assessed based on the following pre-qualification criteria. The bidder is required to produce the copies of the required supportive documents / information as part of their technical proposal failing which the proposals will be rejected.

| Sr. No. | Pre-Qualification Criteria | Specific Requirement | Documents Required |
| --- | --- | --- | --- |
| 1 | Legal Entity | The Sole Bidder or Consortium partners (Not more than 2) must be registered as either of the following: - Company under Companies Act, 1956/2013 or - Partnership Firm registered under the Indian Partnership Act, 1932 or - Limited Liability Partnership registered under The Limited Liability Partnership Act, 2008 registered | Registration documents of the Bidder as a duly registered legal entity in India along with: - Registration document showing incorporation of the Bidder - Certified copy of registered Partnership Deed - PAN Card of the registered legal entity, - GST certificate of the registered legal entity |
| 2 | Operation | The Sole Bidder or Consortium partners should have been in working IT/ITeS services for the past 05 (Five) years as on the date of issue of RFP and filed ITRs for the last three FYs (i.e., FYs 2022-23, 2023-24 & 2024-25) | Audited Financial Statements for the last three financial years duly sealed & signed by a Chartered Accountant in practice, along with ITR for the said periods and the latest GST Return (GSTR-3B). Provisional Audit Report for any of the FYs will not be accepted. |
| 3 | Financial Capacity | The Sole Bidder shall have an average annual turnover of at least Rs. 75 Crore over the last three Financial Years i.e., FY: 2022-23, 2023-24 & 2024-25 from IT/ITeS services. In case of consortium the Lead Bidder should shall have an average annual turnover of at least Rs. 60 Crore over the last three Financial Years i.e., FY: 2022-23, 2023-24 & 2024-25 and consortium partner shall have an average annual turnover of at least Rs. 15 Crore over the last three Financial Years i.e., FY: 2022-23, 2023-24 & 2024-25 from IT/ITeS services. | Audited financial statements/CA certified true copy stating the turnover. Financial Details of the bidder along with copies of last three FY’s Audited Financial Statement duly sealed &signed by a Chartered Accountant in practice with Registration Number |
| 4 | Net Worth | Sole Bidder and Consortium partners should have positive networth over the last three Financial Years i.e., FY: 2022-23, 2023-24 & 2024-25. | A Certificate duly sealed & signed by a Chartered Accountant in practice with Registration Number |
| 5 | ISO Certificate | Sole Bidder and Lead Bidder in case of Consortium should have ISO 9001, ISO 14001 & ISO 45001 certification. | Copy of valid ISO certificates of the agency/ the OEM must be submitted. |
| 6 | Similar Experience | The Sole Bidder or Lead Bidder of consortium, during last 05 (Five) financial years, must have the experience of setting up, training and running ICT Labs* with any Government organization/ any Education Institutions with following minimum order value. - Experience in execution of Single Work Order with minimum order value of Rs. 5 Crore or above, Or - Experience in execution of at least 02 (Two) Work Orders with minimum order value of Rs.3.50 Crore or above Or - Experience in execution of at least 03 (Three) Work Orders with minimum order value of Rs.2 Crore or above In case of consortium the Consortium Partner other than Lead Bidder should have an experience of providing training/ awareness program/ capacity building in any IT project with any Government organization | Copies of Work Orders / Agreement and client certificate for completion of project Note: Projects with more than 12 months duration shall be accepted in case of ongoing projects along with Work Orders / Agreement and client certificate |
| 7 | Mandatory Documents | The bidder shall submit the Technical data in compliance with the minimum technical specifications mentioned in the tender document (ToR) and Manufacturer Authorization Form (MAF) | 1. Submission of product wise brochure & catalogues and relevant pages from the website with available technical data in compliance with the minimum technical specifications mentioned in the ToR. 2. Manufacturer Authorization Form (MAF) from Original Equipment Manufacturer (OEM) for the products proposed. |
| 8 | Blacklist | The Sole bidder and Consortium members shall not have been blacklisted by any Central / State Government Ministry in India or Public Sector Undertakings or any Government Agencies. Any Bidder that has been barred by the Central Government, any State Government, a statutory authority, or a Public Sector Undertaking from participating in any project and the bar subsists as on the date of the Proposal Due Date, would not be eligible to submit a Proposal. | Undertaking by the Authorized Signatory |
| 9 | Consortium/ Joint Venture | In case of consortium a consortium agreement needs to be submitted mentioning the roles and responsibilities of each member of consortium | Original agreement (Notarized on a Rs.100/- Non-Judicial Stamp Paper) |
| 10 | Authorized Representative | A Power of Attorney in the name of the person signing the proposal. | Original Power of Attorney (Notarized on a Rs.100/- Non-Judicial Stamp Paper) |
| 11 | Bid Processing Fee (Non-Refundable) | Rs. 10,000/- to be paid online on eProcurement portal). | to be paid online on eProcurement portal |
| 12 | Earnest Money Deposit (EMD) | Rs. 5,00,000/- to be paid online on eProcurement portal | to be paid online on eProcurement portal |

*Note- ICT Labs means - Computer Labs/ AI Labs / Data Labs / IT Skill Development Labs / Emerging Technology Labs/ ICT Lab for any Digital Transformation project

### Evaluation of Proposals

A Three stage evaluation process will be conducted as explained below for evaluation of the proposals:

### Preliminary Evaluation (1st Stage):

Preliminary evaluation of the proposals will be done to determine whether the proposal complies with the prescribed eligibility condition and the requisite documents / information have been properly furnished by the bidder or not. Submission of documents/ information as per Pre-Qualification/Eligibility Criteria will be verified.

The bidder is required to produce the copies of the required supportive documents/information as part of their technical proposal failing which the proposals will be rejected.

### Technical Evaluation (2nd Stage):

Technical proposal will be opened and evaluated for those bidders who qualify the preliminary evaluation stage. Detailed evaluation process as per the following parameters will be adopted for proposal evaluation:

| Sl. No. | Criteria | Maximum Mark | Documents Required |  |
| --- | --- | --- | --- | --- |
| 1 | Financial Capacity & Experience | 60 Marks |  |  |
| 1.1 | The Sole Bidder or Consortium partner jointly shall have an average annual turnover of at least Rs. 75 Crore over the last three Financial Years i.e., FY: 2022-23, 2023-24 & 2024-25 from IT/ITeS services. Scoring Criteria: - Rs. 75 crore and less than Rs. 100 Crore- 5 Marks - Rs. 100 Crore and less than Rs. 150 Crore- 10 marks - More than Rs. 150 Crore- 15 marks | 15 | Audited financial statements/CA certified true copy stating the turnover. Financial Details of the bidder along with copies of last three FY’s Audited Financial Statement duly sealed &signed by a Chartered Accountant in practice with Registration Number |  |
| 1.2 | Past Experience: The Sole Bidder or any member of consortium, during last 05 (Five) financial years, must have the experience of setting up, training and running ICT Labs with any Government organization/ any Education Institutions with following minimum order value. of Rs. 5 Crore or above, Scoring Criteria: - For every work order value of Rs. 5 Crore or more: 5 Marks will be given. - For every work order value of Rs.3.5 Crore or more but less than Rs.5 Crore: 2.5 Marks will be given. (A bidder can submit maximum up to 3 projects and maximum marks is 15 ) | 15 | Copies of Work Orders / Agreement and client certificate for completion of project Note: Projects with more than 12 months duration shall be accepted in case of ongoing projects along with Work Orders / Agreement and client certificate |  |
| 1.3 | The Sole Bidder or members of consortium jointly, during last 05 (Five) financial years, must have the experience of setting up, training and running ICT Labs with any Government organization/ any Education Institutions the number of project 3 Projects-5 marks 4 Projects-10 marks 5 Projects-15 marks | 15 | Copies of Work Orders / Agreement and client certificate for completion of project Note: Projects with more than 12 months duration shall be accepted in case of ongoing projects along with Work Orders / Agreement and client certificate |  |
| 1.4 | The Sole Bidder or members of consortium jointly, during last 05 (Five) financial years, must have the experience of setting up, training and running ICT Labs with any Government organization/ any Education Institutions the number of trainees trained in maximum 3 projects 100 trainees -5 marks 101- 200 trainees - 10 marks More than 200 trainees -15 marks | 15 | Copies of Work Orders / Agreement and client certificate for completion of project Note: Projects with more than 12 months duration shall be accepted in case of ongoing projects along with Work Orders / Agreement and client certificate Note- Documentary evidence supporting the number of trainees trained |  |
| 2 | Technical Proposal and Presentation | 40 Marks |  |  |
| 2.1 | Technical Proposal mentioning the Proposed Setup, Quality, Events like Hackathons, Training, Assessment & Certification from reputed institutions & Placement, Project Management as per scope of work | 40 | Each bidder needs to submit the technical proposal with the bid and qualified bidders will be required to give a presentation of around 30 minutes on the proposal. |  |
|  | Grand Total (1 + 2) | 100 |  |  |
| - The minimum qualifying mark is: 70 - Bidder must score at least 70% to qualify for opening of Financial Bid. - The scores provided by the Technical Committee will be considered as final. - The Technical Committee will assess the bidders capabilities through for a brief Technical PPT presentation on Bidder’s proposals includes description of products make, model & proposed specifications of items in their Technical Proposal, past experience, objective, proposed plan, approach and methodology etc. |  |  |  |

### Evaluation of Financial Proposal (3rd Stage)

Empanelment and Rate Discovery Mechanism

- Empanelment Model

- CHiPS intends to empanel multiple agencies for Design, Supply, Installation, Commissioning, Training, Operation and Maintenance of AI Labs in Government ITIs and other institutions across Chhattisgarh.

- The empanelment shall be based on a Least Cost (L1) Rate Contract Model.

- The objective of empanelment is to create a pool of technically qualified agencies capable of undertaking AI Lab projects across the State.

- Technical Qualification

- All bidders securing the minimum qualifying marks in the Technical Evaluation Criteria shall be declared Technically Qualified.

- Only technically qualified bidders shall be considered for opening of financial proposals.

- Financial Evaluation

The financial proposals shall be opened on the prescribed date in the presence of the bidder/bidder’s representative who wishes to attend the meeting with proper letter of authorization. The name of the bidder along with the quoted financial price will be announced during the meeting.

- The financial bids of bidders whose bids have been technically qualified (i.e., obtained minimum 70 marks in Technical Evaluation) shall be opened by the Committee on the date and time specified in the RFP.

- Least Cost Selection (LCS) method will be followed during the Financial Evaluation and overall selection process.

- Price Quoted without tax (as applicable) for ‘Total Cost of Goods’ will be considered for Evaluation of the Financial Bid Evaluation.

- If a tenderer submits a bid with what appears to be predatory pricing or an abnormally low bid, the Tender Evaluation Committee may request a written clarification from the bidder. The bidder will be asked to provide a detailed price analysis, price break up, or justification of the quoted price, considering the scope, schedule, risk allocation, and any other requirements outlined in the tender documents. If, after reviewing the price analysis or justification, the bidder fails to provide adequate supporting documentation, evidence, or calculations to substantiate the quoted price, the Committee may, at its sole discretion, reject the bid.

- The bidder quoting the lowest evaluated price (L1) shall be identified.

- The L1 rates shall become the Approved Empanelment Rates.

- Rate Matching By Other Bidders

- All technically qualified bidders shall be offered an opportunity to match the L1 rates.

- The bidders willing to match the L1 rates shall submit an unconditional acceptance in the prescribed format within the timeline specified by CHiPS.

- Upon acceptance, such bidders shall also be empaneled at the approved L1 rates.

- Empaneled Agencies

The following categories of agencies shall be empaneled:

a) L1 Bidder

b) Technically Qualified Bidders who agree to match the L1 rates

Maximum 5 agencies shall be empaneled for project allocation purposes.

- Failure To Match L1 Rates

- Any technically qualified bidder that refuses or fails to match the L1 rates within the stipulated time shall not be empaneled.

- CHiPS shall have no obligation to seek further clarification or negotiations.

- Rate Contract

- The approved L1 rates shall remain valid for the entire empanelment period of 5 year unless revised by mutual agreement.

- The empaneled agency shall not quote rates higher than the approved rates during the empanelment period.

- Project Allocation Mechanism

- Work Orders may be issued to empaneled agencies through any of the following mechanisms:

  - EOI among Empaneled Agencies

  - Project-Specific Requirement-Based Allocation

- The decision of CHiPS shall be final and binding.

- Preference In Allocation

- CHiPS may allocate work based on:

- Past performance

- Availability of resources

- SLA compliance

- No empaneled agency shall have exclusive rights over any district, region or institution.

- Performance Review

Empaneled agencies shall be evaluated periodically based on:

• Timely implementation
• Infrastructure quality
• Training outcomes
• Placement outcomes
• SLA compliance
• User satisfaction

Poor performance may lead to reduction in future work allocation.

- Right To Empanel Multiple Agencies

CHiPS reserves the right to empanel one or more agencies at matched L1 rates to ensure:

• Wider geographical coverage
• Faster implementation
• Risk mitigation
• Availability of backup agencies

- No Guarantee Of Business

- Empanelment does not guarantee award of any minimum quantity of work.

- CHiPS reserves the right to allocate work among empaneled agencies based on project requirements and performance.

- Performance Security

For each work order, the selected empaneled agency shall furnish a Performance Bank Guarantee equal to 10% of the work order value.

- Validity of Rates

The approved L1 rates shall remain valid for a period of five (5) years from the date of empanelment unless otherwise extended by CHiPS.

Other Terms and Conditions:

### Anti-corruption Measure:

- Any effort by Bidder(s) to influence the Client in the evaluation and ranking of financial Bids, and recommendation for award of contract, will result in the rejection of the Bid.

- A recommendation for award of Contract shall be rejected if it is determined that the recommended bidder has directly, or through an agent, engaged in corrupt, fraudulent, collusive, or coercive practices in competing for the contract in question. In such cases, the Client shall blacklist the bidder either indefinitely or for a stated period of time, disqualifying it from participating in any related bidding process for the said period.

### Force Majeure

“Force Majeure” means an event which is beyond the reasonable control of a Party, and which makes a Party’s performance of its obligations here under impossible or so impractical as reasonably to be considered impossible in the circumstances, and includes, but is not limited to, war, riots, civil disorder, earthquake, fire, explosion, storm, flood or other adverse weather conditions, strikes, lockouts or other industrial action (except where such strikes, lockouts or other industrial action are within the power of the Party invoking Force Majeure to prevent), confiscation or any other action by government agencies.

Force Majeure shall not include: (i) any event which is caused by the negligence or intentional action of a Party or agent’s employees thereof, nor (ii) any event which a diligent Party could reasonably have been expected to take into account or avoid or overcome in the carrying out of its obligations during the subsistence of this Agreement. Force Majeure shall not include insufficiency of funds or failure to make any payment required hereunder.

### Language of Proposals:

The proposal and all related correspondence exchanged between the bidder and the Client shall be written in the English language. Supporting documents and printed literature that are part of the proposal may be in another language provided they are accompanied by an accurate translation of the relevant passages in English with self-certification for accuracy, in which case, for the purposes of interpretation of the Proposal, the translated version shall govern.

### Cost of bidding:

The Bidder shall bear all costs associated with the preparation and submission of its proposal. The Client shall not be responsible or liable for those costs, regardless of the conduct or outcome of the bidding process. Bidder/s is/are not allowed to submit more than one proposal under the selection process. Alternate bids are also not allowed.

### Legal Jurisdiction:

All legal disputes are subject to the jurisdiction of competent court of Chhattisgarh only.

### Governing Law and Penalty Clause:

The schedule given for delivery is to be strictly adhered to in view of the strict time schedule. Any unjustified and unacceptable delay in delivery shall render the bidder liable for liquidated damages and thereafter the Client holds the option for cancellation of the contract for pending activities and complete the same from any other Bidder. The Client may deduct such sum from any money from their hands due or become due to bidder. The payment or deduction of such sums shall not relieve the bidder from his obligations and liabilities under the contract. The rights and obligations of the Client and the bidder under this contract will be governed by the prevailing laws of Govt. of India/ Chhattisgarh.

### Client’s right to accept any Bid, and to reject any or all Bid/s

The Client reserves the right to accept or reject any Bid, and to annul or amend the bidding / selection / evaluation process and reject all Bids at any time prior to award of contract award, without assigning any reason there of and thereby incurring any liability to the bidders. Misrepresentation/improper response/ by the bidder may lead to the disqualification of the bid. If such disqualification/rejection occurs after the Bids have been opened and the highest-ranking bidder gets disqualified/rejected, then the client reserves the right to consider the next best bidder, or take any other measure as may be deemed fit in the sole discretion of the Client, including annulment of the selection Process.

### Number of Bids:

Each Bidder shall submit only one (1) Bid, in response to this RFP. Any Bidder who submits or participates in more than one Bid shall be disqualified. The Bidder shall be responsible for all costs associated with the preparation of its Bid and its participation in the bidding process.

### Amendment of the RFP Document:

At any time before submission of proposals, the Client may amend the RFP by issuing an addendum through Department website. Any such addendum will be binding on all the bidders. To give bidders reasonable time in which to take an addendum into account in preparing their proposals, the Client may, at its discretion, extend the deadline for the submission of the proposals.

### Confidentiality:

Information relating to evaluation of proposals and recommendations concerning awards shall not be disclosed to the bidders who submitted the proposals or to other persons not officially concerned with the process, until the publication of the award of contract. The undue use by any Consultant of confidential information related to the process may result in rejection of its proposal and may be subject to the provisions of the Client’s antifraud and corruption policy. During the execution of the assignment except with prior written consent of the Client, the consultant or its personnel shall not at any time communicate to any person or entity any confidential information acquired in the course of the contract.

### Settlement of Dispute:

The Client and the Bidder shall make every effort to resolve amicably, by direct negotiation, any disagreement or dispute arising between them under or arising from or in connection with the contract. All claims and disputes arising under or relating to this Agreement are to be settled by binding arbitration in the state of Chhattisgarh. An award of arbitration may be confirmed in a court of competent jurisdiction. Arbitration shall be as per Indian Arbitration Act, 1996.

Disputes not so resolved amicably within 30 days of receipt of notice of such as a dispute shall be resolved by Secretary E&IT Department, Government of Chhattisgarh which is binding and final.

### Disqualification of Proposal:

The proposal is liable to be disqualified in the following cases as listed below:

- Proposal submitted without Bid Processing Fee & EMD as applicable

- Proposal not submitted in accordance with the procedure and formats as prescribed in the RFP

- During validity of the proposal, or its extended period, if any, the bidder increases his quoted prices

- Proposal is received in incomplete form

- Proposal is received after due date and time for submission of bid

- Proposal is not accompanied by all the requisite documents / information

- A commercial bid submitted with assumptions or conditions

- Bids with any conditional technical and financial offer

- If the bidder provides any assumptions in the financial proposal or qualifies the commercial proposal with its own conditions, such proposals will be rejected even if the commercial value of such proposals is the lowest / best value

- Proposal is not properly sealed or signed

- Proposal is not conforming to the requirement of the scope of the work of the assignment.

- Bidder tries to influence the proposal evaluation process by unlawful/corrupt/fraudulent means at any point of time during the bid process

- If, any of the bid documents (including but not limited to the hard and soft/electronic copies of the same, presentations during evaluation, clarifications provided by the bidder), excluding the commercial bid, submitted by the bidder is found to contain any information on price, pricing policy, pricing mechanism or any information indicative of the commercial aspects of the bid;

- Bidders or any person acting on its behalf indulges in corrupt and fraudulent practices

- Any other condition / situation which holds the paramount interest of the Client during the overall section process.

### Fraud and Corrupt Practices

The Bidders and their respective officers, employees, agents and advisers shall observe the highest standard of ethics during the Bidding Process. Notwithstanding anything to the contrary contained herein, CEO, CHIPS may reject a Bid without being liable in any manner whatsoever to the Bidder, if it determines that the Bidder, directly or indirectly or through an agent, engaged in corrupt practice, fraudulent practice, coercive practice, undesirable practice or restrictive practice in the Bidding Process. In such an event, CEO, CHIPS shall be entitled to forfeit and appropriate the Bid Security or Performance Security, as the case may be, as Damages, without prejudice to any other right or remedy that may be available to CEO, CHIPS under the Bidding Documents and/ or the Agreement, or otherwise.

Without prejudice to the rights of the CEO, CHIPS herein above and the rights and remedies which CEO, CHIPS may have under the RFP, or otherwise if a Bidder is found to have directly or indirectly or through an agent, engaged or indulged in any corrupt practice, fraudulent practice, coercive practice, undesirable practice or restrictive practice during the Bidding Process such Bidder, at the sole and absolute discretion of CEO, CHIPS, shall not be eligible to participate in any tender or RFP issued by CEO, CHIPS during a period of 2 (two) years from the date such Bidder, is found to have directly or indirectly or through an agent, engaged or indulged in any corrupt practice, fraudulent practice, coercive practice, undesirable practice or restrictive practices, as the case may be. The following terms shall have the meaning hereinafter respectively assigned to them.

### SECTION III: Terms of Reference (ToR)

- Introduction:

Chhattisgarh Infotech Promotion Society (CHiPS), Government of Chhattisgarh intends to empanel eligible agencies for setting up and operating Artificial Intelligence (AI) Labs in Government Industrial Training Institutes (ITIs) across the State.

The empaneled agencies shall establish AI Labs on a turnkey basis and operate them for a period of three (3) years including infrastructure, equipment, software, trainers, curriculum delivery, certification support and industry engagement.

The project shall align with IndiaAI Mission, FutureSkills initiatives, NCVET-approved AI curricula and industry requirements.

The goal of the project is to impart quality skill development training to build a knowledgeable workforce to cater to the demand of the labour market. Additionally, generation of such industry- ready manpower would ensure India’s competitiveness in the global market.

### Objective:

  - To expose students to foundational level courses in AI like Data Curation, Annotation and others

  - To help them understand the impact of AI in specific domains like healthcare, education, agriculture and manufacturing.

  - Build an ecosystem of learning, collaborating and developing solutions for the real world use cases.

  - Also build a pool of trainers in teaching AI related courses.

### Scope of the Project

A- Scope of CHIPS/ Institutions (the Buyer/Client):

The scope of work inter alia states that;

- Institutions shall provide required space in the lab for the installation & commissioning of the AI Lab equipment/software within its premises.

- Facilitate additional space (covered area) if required upon availability at the institute premises at free of cost.

- Provide basic amenities like approach road and internet connectivity nearest to the lab for running the AI Lab equipment/software. Three phase electrical connection (if required) at nearest distribution/panel board will be provided at the designated labs by the consignee institutes. Internet and Electricity Charges shall be borne by Institutions.

- Conduct Pre-Delivery Inspection of sample AI Lab equipment/software through Physical mode by its own technical experts or 3rd party agency/consultants/advisors appointed by CHIPS before the proposed AI Lab equipment/software dispatch by the selected bidder and Post Delivery Inspection of all supplied AI Lab equipment/software by its own technical experts or by an independent agency appointed by CHIPS at any point of time. The operational expenses like testing the machines/equipment will be borne by the supplier.

- Consignee institutes will be responsible to monitor the performance of the supplied AI Lab equipment/software and progress of the work.

### B- Scope of the Successful Bidder:

  - Supply, installation and commissioning of all AI Lab equipment/software etc. in compliance to the technical specifications mentioned in the RFP, will be done by the Selected Bidders at the consignee institutes. Partial bidding/supply will not be accepted.

  - All items mentioned in this tender should be of Original OEM. No Compatible or Duplicate/Refurbished items will be accepted. The bid shall be out rightly rejected.

  - The CHIPS reserves the right to increase/decrease the ordered quantity by up to 25 per cent at any time, till the final delivery date (or the extended delivery date of the contract), by giving reasonable notice to the supplier without any change in the final agreed price.

  - After the supply of BoQ items, the successful bidder has to execute its installation & commissioning in the designated site(s) at the address. No extra cost shall be paid for this purpose.

  - Selected Bidder is responsible for all necessary works including necessary civil works (if any), electrical connections from nearest distribution panel board to the supplied AI Lab and all type of cables connections, circuit breakers etc. required for connecting power supply point to machines, and other requisite works to complete the installation of the supplied AI Lab equipment/software at the Consignee Institutes, falls within the ambit of scope of work of selected bidder.

  - Required Room/space will be provided by the Consignee Institutes but Selected Bidder is expected to supply all other installation accessories, facilities and services required for successful installation and smooth operation of the supplied AI Lab equipment/software.

  - Any accessories that must be needed for operation of the AI Lab equipment/software but not mentioned in the specification shall also be quoted by the selected bidder.

  - Suitable and essential tool kit is to be supplied by the selected bidder with the AI Lab equipment/software for the required maintenance.

  - The AI Lab equipment should be installed and commissioned at site. Site requirement along with the layout drawing for installation of required AI Lab equipment/software, electrical connection from main/ nearest sources shall be provided by the selected bidder upon issuance of Letter of Award of Contract (LoA).

  - The selected bidder shall provide comprehensive warranty of supplied AI Lab equipment/software for minimum 03 years from the date of successful commissioning.

  - Provide handholding for 36 months from the date of successful commissioning. Deployment of at least one trainer and on lab assistant for minimum 36 months to provide hand-holding training for the nominated trainees. Training of minimum 180 number of candidates for courses on AI & Data Sciences over a period of 3 years.

Detailed Scope of Work

1. Site Survey and Design

The agency shall:

• Conduct detailed site assessment.
• Verify available space.
• Assess electrical load requirements.
• Assess internet and network connectivity.
• Assess safety requirements.
• Prepare site readiness report.
• Prepare detailed layout drawings.
• Prepare electrical and networking diagrams.
• Obtain approval from CHiPS.

2. Civil Works and Interiors

The agency shall undertake complete civil works including:

2.1 Interior Development

• False ceiling.
• Vinyl flooring/anti-static flooring.
• Painting and wall finishing.
• Branding and graphics.
• AI-themed wall panels.
• Acoustic treatment where required.
• Modular partitions.

2.2 Space Development - Refer Annexures 1 & 2 for Layout Options

a. Learning Zone

This space where students begin their skilling journey and develop foundational concepts by engaging in hands-on activities, experiments and discussions. The 18 seats are expected to be arranged in a manner that enables all students to be seated together.

b. Collaborative Zone

The space is for brainstorming and collaborative thinking. Its purpose is to create an environment that fosters learning, sharing and working together amongst learners. It just consists of a table (preferably round) and 4 chairs around it.

c. Development and Inferencing Zone

This 2 seater space consists of 2 high end GPUs where the students extensively work on programming and AI modelling; where they test their AI enabled solutions, develop them into working prototypes and work on a simulated virtual apprenticeship platform solving real time industry problems.

2.3 Signage and Branding

• IndiaAI branding.
• Government of Chhattisgarh branding.
• CHiPS branding.
• Lab usage guidelines.
• Safety instructions.

3. Electrical Works

The agency shall undertake complete electrical works including:

• Internal wiring.
• Power distribution boards.
• Dedicated circuits.
• Earthing.
• Power sockets.
• Conduits and raceways.
• LED lighting.
• Surge protection.
• Electrical safety equipment.

The agency shall obtain all required safety certifications.

4. Air Conditioning

The agency shall provide:

• High-efficiency inverter air conditioners.
• Capacity as per room size.
• Copper piping.
• Stabilizers.
• Drainage arrangements.

Temperature shall be maintained suitably for AI servers and workstations.

5. UPS and Power Backup

The agency shall provide:

• Online UPS systems.
• Minimum 60-minute backup.
• Battery bank.
• Power conditioning systems.
• Network rack power systems.

6. Networking Infrastructure

The agency shall provide:

• Structured CAT-6/CAT-6A cabling.
• Network racks.
• Managed switches.
• Wi-Fi access points.
• Firewall.
• Internet integration.
• Network monitoring tools.

7. AI Lab Infrastructure

As per BOQ

All assets procured under the project shall become property of Government of Chhattisgarh from the date of acceptance.

8. Curriculum Delivery

The agency shall deliver:

| S. No. | Name of course* | Duration | Batch Size | Per day | No. of batches per year |
| --- | --- | --- | --- | --- | --- |
| 1 | Data Annotator Assistant | 120 Hours (Theory 40 hrs +Practical 80 hrs.) | 20 students | 2 hrs | Min 1 |
| 2 | Data Curator Assistant | 120 Hours (Theory 40 hrs +Practical 80 hrs.) | 20 students | 2hrs. | Min 1 |

*Refer Annexures 3 & 4 for Course details

Minimum 60 students to be trained in 1 year and 180 students in 3 years.

If a student drops out within first 25% of course duration, institution may nominate a replacement candidate without additional cost.

The 3rd part agency shall conduct the exam on the course tought by the bidders.

9. Trainer Deployment

Per Lab:

• 1 Full-Time AI Trainer- The trainer/expert must have a Bachalor’s or Master’s degree in Data Science or Computer Science, Data Analytics or a in a related field with minimum 3 years of relevant industry experience

• 1 Lab Assistant- The Lab Assistant must have a Bachalor’s degree in ITs or in a related field with minimum 1 years of relevant industry experience

10. Operations Management

The agency shall:

• Manage daily operations.
• Maintain attendance.
• Manage LMS.
• Conduct assessments.
• Manage certifications.
• Organize events.
• Maintain assets.

11. Innovation and Industry Connect

Agency shall conduct annually:

• Hackathons
• AI Innovation Challenges
• Industry Sessions

12. Internship and Placement

Agency shall:

• Facilitate internships.
• Organize placement drives.
• Conduct interview preparation.
• Engage industry partners.

13. Maintenance

The agency shall provide:

• Preventive maintenance.
• Corrective maintenance.
• Hardware replacement.
• Software updates.
• Antivirus updates.
• Security patches.

14. Project Management

Agency shall establish:

• State Project Manager

15. Reporting

Monthly Reports:

• Training status
• Infrastructure status
• Student enrolment
• Certifications
• Placement progress

Quarterly Reports:

• Innovation activities
• Industry engagement
• Utilization reports

16. Handover

Upon completion of the contract period, all assets, software configurations, documentation and training materials shall be handed over to CHiPS/ Institutions in working condition without additional cost.

17. Subcontracting

- General

- The Empaneled Agency shall be solely responsible for the execution of the Project and fulfillment of all contractual obligations under the Contract.

- The Empaneled Agency shall not assign, transfer, sublet or subcontract the whole or any part of the Contract without prior written approval of CHiPS.

- Permitted Subcontracting

The Empaneled Agency may engage specialized subcontractors for execution of the following activities only:

a) Civil Works

b) Interior Works

c) Furniture Manufacturing and Installation

d) Electrical Works

e) Air Conditioning (HVAC) Works

f) Structured Cabling and Passive Networking

g) Signage and Branding Works

Provided that:

i. The Empaneled Agency shall obtain prior written approval from CHiPS.

ii. The Empaneled Agency shall submit details of the proposed subcontractor, including experience, technical capability and statutory registrations.

iii. The subcontractor shall comply with all applicable labour, tax and statutory requirements.

### C- Pre-Delivery Inspection and Post-Delivery Inspection of all equipment:

CHIPS/ Institutions may conduct a Pre-Delivery inspection of all equipment or software/sample equipment or software through Physical mode by its own technical experts or 3rd party agency/consultants/advisors appointed by CHiPS before the dispatch of the proposed equipment by the selected bidder at the supplier’s premises or at the manufacturer’s factory site. The operational charges i.e. testing charges for samples, raw material (if any), consumables (if any) etc. shall be borne by the supplier. But, other expenses like travelling, boarding and lodging of the technical experts, will be borne by the Authority.

All tests and inspections of all equipment/software during Post-Delivery Inspection shall be made at the place of delivery. Officers authorized by CHIPS/ Institutions shall be entitled at all reasonable time to inspect and supervise and test during installation and commissioning. Such inspection will not relieve the selected Bidder of their obligation in the contract.

If the Bidder fails to comply with any of the quality, technical specification or clause mentioned in the RFP, and then the Contract will be terminated by CHIPS.

# Special Terms and Conditions:

- Bidder must provide necessary documentary evidence from an Original Equipment Manufacturer of the related equipment. Bid specific authorisation must be submitted from OEM.

- An undertaking from the OEM is required stating that they would facilitate the Bidder on a regular basis with technology/product updates and extend support for the warranty as well.

- Bidder has to quote for all BoQ equipment/software as per RFP. Partial bidding is not allowed.

- The supplier of the equipment must confirm in writing that the spares for the entire supplied equipment will be available for a period of at least five years after the model of equipment supplied has been phased out. For frequently required spares, there should be adequate inventory with the Indian agency.

- The successful bidder is responsible for the supply, installation and maintenance of the equipment. Equipment documentation including user manuals and operation and troubleshooting guides to be provided.

- Comprehensive Warranty period shall specifically be mentioned in the offer. The selected bidder must adhere to the warranty clause mentioned herein.

- Bidder must enclose the undertaking regarding the Software, Firmware updation, or upgradation required by CHIPS/ Institutions without any extra cost.

- OEM should have same made of Monitor, CPU, Mouse and Keyboard. OEM LOGO/trademark should be embossed on them (No sticker will be accepted).

- Certification:- TCO 8.0 certification for Monitor, Energy Star 7.0 or higher, EPEAT/EPR certificate, ROHS certificate must be uploaded.

- Bidder must upload undertaking from the OEM regarding the preloaded Operating System.

- Financial Proposal must be submitted as per the BoQ MS-Excl format along with formats shared in FIN-1 & Annexure (PDF file).

- Bidders must submit Technical Specification Compliance sheet within their technical bid. The bidders must be kept in their mind that mere copying of our specifications in the technical specification compliance sheets, shall not make the technical bid eligible for consideration. A bid has to be supported with original catalogue of the quoted item/s duly signed by the authorized person participating in the bid. Non-compliance with the above conditions shall be treated as incomplete/ambiguous and the bid shall be rejected without giving an opportunity to the bidder for further clarification/negotiation etc.

- Bidder must quote Cost of the Goods, which shall indicate clearly the including all taxes and charges towards packing, forwarding, handling, insurance, comprehensive warranty for 36 months, freight, incidental service, civil, electrical and other works, (if any), installation & commissioning of the goods and training to the consignee’s personnel at site. The price shall be quoted in Indian Rupees only.

- The cost of standard accessories shall be included in basic price and optional accessories shall have to be quoted separately.

- Any component, fitting etc. which may not have been specifically mentioned in the specifications but which are usual and necessary for the equipment, shall be supplied by the bidder at no extra cost.

- In case of items of import, the bidder should take full responsibility for customs clearance, handling, tax payment, etc. and same should be inclusive in the financial bid.

- CHIPS reserves the right to increase/decrease the ordered quantity by up to 25 per cent at any time, till the final delivery date (or the extended delivery date of the contract), by giving reasonable notice to the supplier without any change in the final agreed price.

- CHIPS reserves the right to accept, split, divide, negotiate, cancel or reject any bid or to annul and reject all bids at any time prior to the award of the contract without incurring any liability to the affected bidders or any obligation to inform affected bidder, the grounds of such action.

- Price bid should be submitted in the given BoQ MS-Excel format and price bid should have equipment wise breakup in FIN-1 & Annexure (PDF file). Price bid should have equipment wise breakup (Annexure).

- Performance Security – A performance security in the form of Bank Guarantee/e-Bank Guarantee for 10% of the Awarded Value (excluding taxes) to be submitted within 15 days of issuance of the Letter of Award (LoA). The Bank Guarantee will be valid initially for 66 months and may be extended further if required. The performance guarantee will be released by CHIPS and returned to the Selected Bidder after 60 days of completion of warranty period subject to fulfillment of all obligations on recommendation of respective Principal of the institutes.

Comprehensive Warranty (36 Months) Clause:

- The final selected bidder must provide Comprehensive Warranty Maintenance Services for all supplied equipment/software (except consumables, & printer) at the consignee institutes for 36 months from the date of successful installation & commissioning. The scope of the bidders is as below.

- Maintenance Services shall consist of Preventive and Corrective maintenance of equipment/software specified in RFP (excluding Consumables, & Printer) & will include repair and replacement of parts free of cost. Warranty for Printers must be given for at least 12 months from the date of successful installation & commissioning.

  - Preventive maintenance, half-yearly once, which includes:

  - Check-up to ensure that device connection is proper; cabling is at proper condition etc.

- Cleaning of the above instruments & equipments and checking the System Performance.

- The selected bidder must conduct preventive maintenance services at least twice (2 times) in a year at the Consignee Institutes.

- The parts replaced must be new parts or equivalent in performance to new parts.

- Any complaint informed through telephone/email must be acknowledged with a Complaint No. by the Supplier which will be noted by Consignee. All further contact with the Supplier on such complaint will be initiated through that Complaint No. Once rectification done, that No. will be cancelled by both parties. A register is to be maintained by the Supplier where complaints are to be noted along with Complaint No.

- The maintenance shall be attended by the service engineer within one week of intimation to the Bidder.

- The Service Engineer of the Supplier will be allowed to handle the respective plant & machineries only in the presence of the officer in charge at the institute site.

- The selected bidder should ensure that maintenance job is not hampered/ delayed due to paucity of spares/inadequate manpower etc.

- Minor repair to be done within 3 days of complaint registered and for major breakdown or replacement of parts must be completed by 15 days from the complaint registered to supplier. For imported parts, the replacement should be done within 4 weeks maximum.

BOQ-List of equipment/machines and their Technical Specifications to be supplied at each institute.

## HARDWARE REQUIREMENT

| CATEGORY | USAGE | DESCRIPTION/SPECIFICATIONS | QTY |
| --- | --- | --- | --- |
| Learning Zone | For Students to access and try program content in Lab Environment | 12th Generation Intel® CoreTMm 15-12500T with Intel vPro® Enterprise 8 GB DDR4- 3200 MHz RAM (1x 8) GB ‘ 512 GB PCleR NVMeTM M.2 SSD ; Intel® UHD; Graphics 770 Windows 11 Professional | 18 Nos. |
| Deep Learning & Inferencing Corner | Workstation for students to perform training and inferencing of deep learning models | 13th Generation Intel® CoreTM 17-13700K (30MB Cache), 16 Core (8+8), 3.40GHz to 5.40GHz (125W))TDP 32GB 2x16GB DDR5 UD , NECC, V2 Nvidia GeForce RTX3070 8GB 2TB PCle NVMe Class 40 M.2 SSD Windows 11 Pro, English | 2 Nos |
| Hardware Kit |  | Jetson Nano with Camera, Wifi dongle and SD Card and other Accessories | 5 Sets |
| Networking |  | Networking equipment like switch, CAT 6 Cable, rack, 9U Jack panel, 1 UPS, IO points+ Supply, Installation, commissioning and testing charges etc. | 1 Set |
| Audio Equipment |  | Audio visual equipment Projector with mount, amplifier, speaker, wireless mic | 1 Set |
| Printer |  | Laser | 1 No. |
| Consumables |  | Pen Drive, SD Card, Removables etc. | 1 Set |
| Software (with Perpetual License) |  | Python Anaconda Distribution Intel® Distribution for Python, OpenVINOTMm Toolkit, OneAPI, Intel® EMA, etc. Al Libraries and Frameworks: TensorFlow, PyTorch, Keras, scikit- learn, CUDA Toolkit for building and training models. Orange Data Mining (Free Version) Tableau (Free version) | 20 Users |
| Office Automation |  |  | 20 |
| AI Trainer (One for 36 months) for training |  |  | 1 |
| Lab Manpower (One for 36 months) for hand-holding |  |  | 1 |

Non-IT Requirements:

| CATEGORY | DESCRIPTION/SPECIFICATIONS | QTY |
| --- | --- | --- |
| Furniture – Workstations and Chair | As per Annexure- III | 20 sets |
| AC | As per Annexure- III | 2 |
| Minor Civil Work | Whitewashing, Lights, Signage, Civil works | Lumpsum |
| Round Table and 4 chairs for collaborative zone | As per Annexure- III | Round Table-1 and Chairs-4 |

## SLA and Penalty

## 1. OBJECTIVE

The purpose of this SLA is to ensure timely implementation, uninterrupted operations, quality training delivery, infrastructure availability, and achievement of project outcomes by the empaneled agency.

The SLA shall remain applicable throughout the implementation period, warranty period, and O&M period.

## 2. SLA CATEGORIES

The SLA shall be monitored under the following categories:

A. Infrastructure Setup SLA

B. Operational SLA

C. Training Delivery SLA

D. Manpower SLA

E. Helpdesk and Support SLA

F. Reporting SLA

G. Placement and Outcome SLA

H. Asset Management SLA

# A. INFRASTRUCTURE IMPLEMENTATION SLA

## 2.1 Site Survey

| SLA Parameter | Requirement |
| --- | --- |
| Site Survey Completion | Within 7 Days of Work Order |

Penalty: ₹5,000 per day per site beyond the stipulated timeline.

Maximum Penalty: 5% of Project Cost.

## 2.2 Lab Establishment

| Activity | Timeline |
| --- | --- |
| Design Submission | 15 Days |
| Civil Works Completion | 45 Days |
| IT Infrastructure Installation | 60 Days |
| Lab Commissioning | 75 Days |
| Go-Live | 90 Days |

Penalty: 0.25% of Work Order Value per week of delay.

Maximum Penalty: 10% of Work Order Value.

# B. INFRASTRUCTURE AVAILABILITY SLA

## 2.3 AI Lab Availability

| Parameter | SLA |
| --- | --- |
| Lab Availability | 99% |

Formula:

Availability = (Total Working Hours – Downtime) / Total Working Hours × 100

Penalty:

| Availability | Penalty |
| --- | --- |
| 98% – 99% | 1% of Quarterly Payment |
| 97% – 98% | 2% of Quarterly Payment |
| Below 97% | 5% of Quarterly Payment |

## 2.4 AI Server Availability

| Parameter | SLA |
| --- | --- |
| GPU Server Availability | 99% |

Penalty: ₹10,000 per incident beyond SLA.

Maximum: 5% of O&M Payment of 5%.

## 2.5 Network Availability

| Parameter | SLA |
| --- | --- |
| LAN | 99% |

Penalty: ₹2,000 per day of outage.

# C. INCIDENT MANAGEMENT SLA

## 2.6 Incident Response

| Incident Type | Response Time | Resolution Time |
| --- | --- | --- |
| Critical | 30 Minutes | 4 Hours |
| Major | 1 Hour | 8 Hours |
| Minor | 4 Hours | 48 Hours |

Critical Incidents:

• AI Server Down • Entire Lab Non-Functional • Security Breach • LMS Failure

Major Incidents:

• Multiple Systems Down • Network Failure

Minor Incidents:

• Single Device Failure • Peripheral Failure

Penalty:

| Severity | Penalty |
| --- | --- |
| Critical | ₹5,000 per incident |
| Major | ₹2,500 per incident |
| Minor | ₹1,000 per incident |

# D. TRAINER DEPLOYMENT SLA

## 2.7 Trainer Availability

| Parameter | SLA |
| --- | --- |
| Trainer Availability | 95% |

Penalty:

₹2,000 per day of trainer absence.

If vacancy remains unfilled beyond 7 working days: ₹5,000 per day.

## 2.8 Lab Assistant Availability

| Parameter | SLA |
| --- | --- |
| Availability | 95% |

Penalty: ₹1,000 per day.

# E. TRAINING DELIVERY SLA

## 2.9 Course Completion

| Parameter | SLA |
| --- | --- |
| Completion of Scheduled Batches | 100% |

Penalty: ₹25,000 per cancelled batch.

## 2.10 Student Attendance

Minimum Average Attendance: 75%

Penalty:

For every 5% shortfall below target: 1% deduction from training payment of 20%.

## 2.11 Assessment Completion

Assessment completion shall be conducted within 15 days of course completion.

Penalty:

₹500 per student delayed.

## 2.12 Certification

Certificates to be issued within 30 days.

Penalty: ₹250 per student per week of delay.

# F. PLACEMENT AND INTERNSHIP SLA

2% deduction from annual performance-linked payment.

# G. REPORTING SLA

## 2.13 Monthly Reports

Reports to be submitted by 5th of every month.

Penalty: ₹2,000 per delayed report per week of delay.

## 2.14 Quarterly Reports

Penalty: ₹5,000 per delayed report per week of delay.

# H. PREVENTIVE MAINTENANCE SLA

## 2.15 Preventive Maintenance

Frequency:

Quarterly

Penalty: ₹10,000 per missed maintenance cycle.

# I. SECURITY SLA

## 2.16 Antivirus and Security Updates

Updates shall be applied within 7 days of release.

Penalty: ₹5,000 per occurrence.

# J. ASSET MANAGEMENT SLA

## 2.18 Asset Verification

Quarterly asset verification mandatory.

Penalty: ₹5,000 per missed verification.

## 2.19 Asset Loss

Replacement: Within 15 Days

Penalty after 15 days: Actual replacement cost as per market value + 10% of market value per month

# K. USER SATISFACTION SLA

## 2.22 Feedback Score

Minimum User Satisfaction Score:

4 out of 5

Penalty:

| Score | Penalty |
| --- | --- |
| 3.5 – 4.0 | 1% deduction of yearly 5% amount |
| 3.0 – 3.5 | 2% deduction of yearly 5% amount |
| Below 3.0 | 5% deduction of yearly 5% amount |

# L. CUMULATIVE PENALTY

Maximum Penalty:

10% of Total Payment

If cumulative penalties exceed: 15% in One year

OR

20% in any Two consecutive years

CHiPS may:

• Suspend work allocation

• Invoke Performance Bank Guarantee

• Issue Show Cause Notice

• Terminate Contract

Timelines and Payment Terms

| Milestone | Basis | Timelines | % of Total Contract Value | Remarks |
| --- | --- | --- | --- | --- |
| Lab Setup & Commissioning | Infrastructure, furniture, electrical, AC, IT assets, trainers deployed | 3 months from the date of issue of Work order | 25% | Acceptance and Sign-off report from the Institution and CHIPS/ TPA |
| Year-1 Batch (60 Students) Completion | Training, assessment, certification | 120 hrs. duration per batch and completion within 3 months from the date of start of batch | Max 20% (Per student basis) | Based on number of students passing the exam and as per the Sign-off report from the Institution and TPA |
| Year-2 Batch (60 Students) Completion | Training, assessment, certification | 120 hrs. duration per batch and completion within 3 months from the date of start of batch | Max 20% (Per student basis) | Based on number of students passing the exam and as per the Sign-off report from the Institution and TPA |
| Year-3 Batch (60 Students) Completion | Training, assessment, certification | 120 hrs. duration per batch and completion within 3 months from the date of start of batch | Max 20% (Per student basis) | Based on number of students passing the exam and as per the Sign-off report from the Institution and TPA |
| O&M, Outcomes & Handover | SLA compliance, O&M, asset management, final reports | Compliance report at the end of each year | 15% | 5% per year based on the Sign-off report from the institution and CHIPS/ TPA |
| Total |  |  | 100% |  |

Annexure-1 Sample Layout Option-1

Annexure-2 Sample Layout Option-2

Annexure-3

Course Curriculum for Data Curator Assistant (120 Hours) Course Title: Data Curator Assistant

Duration: 120 Hours

Minimum Education Qualifications- 10th Pass Level: Intermediate

Delivery Mode: Classroom/ Online Course Objectives:

The primary objective of the Data Curation Assistant course is to provide learners with comprehensive knowledge and practical skills in managing, organizing, and maintaining data throughout its lifecycle. This includes data collection, cleaning, annotation, integration, storage, quality control, and visualization. The course aims to prepare learners for careers in data curation, enabling them to ensure data quality, compliance with ethical standards, and effective data utilization for decision-making and analysis.

- Equip students with essential data curation skills.

- Provide foundational knowledge in data collection, cleaning, integration, and storage.

- Develop soft skills necessary for effective teamwork and communication.

- Ensure understanding of data quality, governance, and ethical considerations.

- Introduce advanced data management techniques and industry tools.

- Enhance practical experience through hands-on projects and case studies.

# Learning Outcomes:

Upon successful completion of the Data Curation course, learners will be able to:

- Python Foundation: Enabling students to write, debug, and execute basic to intermediate-level Python programs, and apply these skills to real-world projects.

- Artificial Intelligence Foundation: AI key components, identify various applications of AI in different industries, Recognize the ethical considerations and challenges associated with AI.

- Understand Data Curation Fundamentals: Define the fundamentals of data curation, including its importance, types of data, and the tools and software used in the process.

- Collect and Acquire Data: Apply various methods and techniques for data collection and acquisition, considering ethical considerations and best practices.

- Clean and Preprocess Data: Perform data cleaning and preprocessing tasks, including handling missing data, applying transformation techniques, and ensuring data normalization and standardization.

- Integrate and Store Data: Implement data integration techniques and manage data storage using data warehousing, database management systems (DBMS), and cloud storage solutions.

- Ensure Data Quality and Governance: Apply quality metrics and governance frameworks to ensure data accuracy, consistency, privacy, and security.

- Visualize and Report Data: Create effective data visualizations and reports using tools like Tableau and Power BI and develop storytelling skills to communicate data insights.

- Complete Real-world Projects: Apply learned skills in real-world projects, collaborate with peers, and present project findings, receiving constructive feedback.

- Prepare for a Career in Data Curation: Explore career opportunities, understand industry trends, and develop a professional resume, with insights from guest lectures and industry experts.

# Module Overview:

| Module Name | Theory (Hours) | Practical (Hours) | Total (Hours) |
| --- | --- | --- | --- |
| Module 1: Introduction to Python | 6 | 12 | 18 |
| Module 2: Python: Advanced | 4 | 8 | 12 |
| Module 3: Artificial Intelligence C Data Science Foundational | 4 | 6 | 10 |
| Module 4: Introduction to Data Curation | 4 | 6 | 10 |
| Module 5: Data Collection C Acquisition Methods | 4 | 6 | 10 |
| Module 6: Data Cleaning and Preprocessing | 4 | 6 | 10 |
| Module 7: Data Integration and Storage | 4 | 6 | 10 |
| Module 8: Data Quality and Governance | 4 | 4 | 8 |
| Module 9: Visualization and Reporting | 2 | 4 | 6 |
| Module 10: Advanced Data Management Techniques | 2 | 4 | 6 |
| Module 11: Practical Projects with Industry | 0 | 16 | 16 |
| Module 12: Soft Skills Training | 2 | 2 | 4 |
| Total | 40 | 80 | 120 |

# Module 1: Introduction to Python

  - Theory (6 Hours)

    - Understanding to set up the Python environment.

    - Learning about variables and different data types in Python.

    - Understanding conditional statements (if, else, elif) and learning about loops (for, while).

    - Understanding the concepts of functions and learning to define and call functions.

# Practical (12 Hours)

    - Learning to install Python and an IDE.

    - Understanding to write and execute simple python scripts such as "Hello, World!”

    - Learning to perform basic operations with variables and data types.

    - Learning to write programs using conditional statements and loops.

    - Learning to create and use functions in Python programs.

# Module 2: Python: Advanced

  - Theory (4 Hours)

    - Understanding the basics of file handling in Python.

    - Understanding python lists (creation, indexing, slicing, etc.) and dictionaries (creation, accessing, etc.), their properties, and uses.

    - Understanding the basics of Python libraries -NumPy, Matplotlib, and Pandas.

# Practical (8 Hours)

    - Learning to read from and write to files using Python.

    - Learning to perform operations with lists and dictionaries in Python.

    - Learning to perform basic operations using various Python libraries.

    - Developing and implementing a project, integrating various concepts learned.

# Module 3: Artificial Intelligence s Data Science Foundational (10 Hours)

  - Theory (4 Hours)

    - Introduction to Artificial Intelligence

      - Understanding the basic concepts and evolution of Artificial Intelligence

      - Understanding the key components of Artificial Intelligence- Machine Learning, Deep Learning, Computer Vision C Natural Language Processing NLP.

      - AI in Healthcare, Finance, Education C Entertainment- Use cases C applications

      - Introduction to Generative AI – tools and use cases.

    - Basic Data Science and Statistics

      - Introduction to Data Science Concepts

      - Learning to handle large C complex datasets

      - Learning	to	implement	data	preprocessing	techniques-	Cleaning, Normalization, Handling Missing Data on sample datasets.

      - Understanding statistical Concepts: Distributions, Variance, Data Sampling

    - Ethical Considerations in AI

      - Introduction to AI Ethics and Biasness in AI models

      - Understanding Privacy Concerns with the use of AI

      - Understanding safe and responsible use of AI

# Practical (6 Hours)

    - Demonstration of popular AI tools

    - Hand on experience on open-source GenAI tools.

    - Demonstration of AI use cases in Healthcare, Finance, Education C Entertainment.

    - Introduction to low-code/no-code AI platforms

    - Various test cases to use preprocessing techniques- data cleaning, normalization, and handling missing data.

# Module 4: Introduction to Data Curation (10 Hours)

  - Theory (4 Hours)

    - Defining Data Curation and understanding the scope of data curation.

    - Evaluating the business needs and understanding the context for which the data is being curated.

    - Case studies showcasing the impact of effective data curation.

    - Learning about various types of Data (Structured, Unstructured, Semi-structured)

    - Learning to examine different types of data available for the data curation process.

    - Characteristics and examples of structured, unstructured and semi structured data.

    - Learning to assess various data sensitivities and ensuring caution while dealing with sensitive, encrypted, masked data

# Practical (6 Hours)

    - Demonstration of features and functionalities of various open-source Data Curation Tools.

    - Hand on experience on popular open-source data curation tools.

    - Learning to examine the data to be curated and identifying any error or missing values in the data.

# Module 5: Data Collection s Acquisition Methods (10 Hours)

  - Theory (4 Hours)

    - Understanding the steps in Data Collection, Defining the goals of Data Collection C understanding what data to be collected

    - Learning about various methods of data collection- Surveys, Observational methods and Experimental Methods- Real-time data collection from sensors, IoT devices, APIs, and social media.

    - Learning to plan the approach- Primary C Secondary data sources

    - Learning about Data Acquisition techniques- Web scrapping, APIs and Data Feeds.Learning about Ethical considerations in Data Collection- Informed consents, Data Privacy C confidentiality, Ethical guidelines and best practices.

# Practical (6 Hours)

    - Understanding various real-world data collection scenarios.

    - Gaining practical experience with popular open-source data collection tools.

    - Hands-on practice sessions focusing on Data acquisition techniques, metadata management and dataset publishing

    - Learning to apply ethical considerations in data collection- informed consent, data privacy and confidentiality, and adherence to ethical guidelines and best practices.

    - Engaging in practical exercises to share and preserve research data through Data Tools.

# Module 6: Data Cleaning and Preprocessing (10 Hours)

  - Theory (4 Hours)

    - Understanding Importance of data cleaning and learning about Common data quality issues.

    - Learning about Data Transformation techniques – Data Normalization, Data Standardization C Data Encoding.

    - Learning about automated data cleaning techniques using AI tools.

    - Learning about Data deduplication, outlier detection, and handling unstructured data.

    - Learning about various Data enrichment techniques- Augmenting with External Data Sources, text enrichment.

# Practical (6 Hours)

    - Practical exercises using data cleaning and preprocessing tools- Talend Wrangler

    - Learning about handling missing data- techniques and Imputation methods

    - Learning the practical exercises for Data Normalization C Data Standardization.

    - Demonstration on automated data cleaning tools.

    - Learning about Data enrichment techniques- Text Enrichment

# Module 7: Data Integration and Storage (10 Hours)

  - Theory (4 Hours)

    - Understanding the concepts C architecture of Data Warehouse

    - Understanding the difference between data lakes and data warehouses

    - Overview of Database Management System

    - Understanding distributed databases and Cloud data governance

    - Introduction to cloud storage solutions- Security C scalability C compliance

# Practical (6 Hours)

    - Learning about various Data Integration techniques- (Extract, Transform, Load) process, Data merging and consolidation

    - Practical exercises using data integration tools.

    - Learning to combine various data from multiple sources into a unified view, for comprehensive analysis and reporting.

    - Demonstration of popular cloud storage solutions

# Module 8: Data Quality and Governance (8 Hours)

  - Theory (4 Hours)

    - Understanding key metrics for assessing data quality and learning techniques for measuring data quality.

    - Learning about techniques to ensure data accuracy and data consistency.

    - Learning about Data Lineage C data cataloging tools

    - Learning about Data governance framework and automation using AI tools.

# Practical (4 Hours)

    - Hand on experience on techniques for maintaining data accuracy and data consistency.

    - Hands on experience on implementing data cataloging tools.

# Module G: Visualization and Reporting (6 Hours)

  - Theory (2 Hours)

    - Understanding various methods C standards to present the data.

    - Introduction to Open-source data visualization tools like Plotly and Matplotlib.

    - Learning about interactive dashboards and real-time reporting techniques for data visualization.

# Practical (4 Hours)

    - Hand on experience on Open-source data visualization tools like Plotly and Matplotlib.

    - Exercises on new templates and real time reporting dashboards for data visualization.

# Module 10: Advanced Data Management Techniques (6 Hours)

  - Theory (2 Hours)

    - Understanding Data governance frameworks along with relevant case studies of successful implementation to provide real world context.

    - Understanding about AI-assisted data curation tools and big data tools.

    - Understanding Cloud based data platforms and data management services.

# Practical (4 Hours)

    - Hands on experience on automated data curation AI tools on multiple tasks- tagging, quality assessments and data integration.

    - Learning to use big data tools and their applications in managing large datasets.

# Module 11: Practical Projects with Industry (16 Hours)

  - Practical (16 Hours)

    - Working on real world Data curation problems sourced from Industry partners.

    - Learning to apply learned skills and knowledge in real world scenario

    - Learning to collaborate and work as a team for common objectives.

    - Presenting the project findings to the peers and instructor and learning to incorporate constructive feedback.

# Module 12: Soft Skills Training (4 Hours)

  - Theory (2 Hours)

    - Learning to explore career paths in Data curation.

    - Communication Skills

    - Problem-Solving Techniques

    - Teamwork and Collaboration

# Practical (2 Hours)

    - Role-playing	exercises	and	group	activities	to	enhance	teamwork	and communication.

# Tools, Equipment and Other Requirements

  - Labs equipped with the following:

    - PCs/Laptops

    - Chart paper and sketch pens

    - Internet with Wi-Fi (Min 2 Mbps dedicated)

# Tools and Programming Languages:

    - Open-source Curation Software/Tools.

    - Open-Source Computer Vision Tools.

    - Open-Source NLP Tools.

    - Documentation tools (Adobe, MS-Word).

    - Documentation tools such as Adobe and MS-Word

    - Whiteboard, markers, LCD projector, laptops.

# Assessment:

    - Continuous assessment through quizzes, peer reviews, and feedback sessions.

    - Final project presentation and evaluation.

***

Annexure-4

Course Curriculum for Data Annotator Assistant (120 Hours) Course Title: Data Annotator Assistant

Duration: 120 Hours

Minimum Education Qualifications- 10th Pass Level: Beginner / Intermediate

Delivery Mode: Classroom/ Online Course Objectives:

The primary objective of the Data Annotation course is to equip learners with the essential skills and knowledge required to perform high-quality data annotation tasks. This includes understanding the fundamentals of Artificial Intelligence (AI) and its domains, mastering various data annotation techniques, and adhering to ethical standards to ensure data quality and minimize bias in AI algorithms. The course aims to prepare learners for careers in data annotation, enabling them to contribute effectively to the development of AI systems.

This curriculum is designed to provide a comprehensive understanding of data annotation, equipping students with the mentioned skills to excel in this field.

- Equip students with essential data annotation skills.

- Provide foundational knowledge in data science and statistics.

- Develop soft skills necessary for effective teamwork and communication.

- Ensure understanding of ethical considerations and data privacy.

- Introduce advanced annotation techniques and industry tools.

- Enhance practical experience through hands-on projects and case studies.

# Learning Outcomes:

Upon successful completion of the Data Annotation course, learners will be able to:

- Python Foundation: Enabling students to write, debug, and execute basic to intermediate-level Python programs, and apply these skills to real-world projects.

- Artificial Intelligence Foundation: AI key components, identify various applications of AI in different industries, Recognize the ethical considerations and challenges associated with AI.

- Apply Computer Basics: Perform installation and customization of operating systems and related software for data annotation purposes, following safety precautions.

- Perform Text Annotation: Execute text annotation tasks accurately and efficiently for data analysis.

- Annotate Audio Content: Make audio content more useful, accessible, and informative for various users and applications through audio annotation.

- Annotate and Label Images and Videos: Annotate and label images and videos to train machine learning models to recognize and classify objects, identify patterns, and make predictions.

- Manage Data Responsibly and Ethically: Follow ethical compliance and utilize data labeling tools effectively, ensuring high-quality annotated data for AI training.

- Understand Data Annotation Tools: Explore various tools such as the Computer Vision Annotation Tool (CVAT) to annotate data for machine learning tasks efficiently.

- Interpret and Transform Data: Learn to clean, interpret, and transform data for analysis, ensuring data quality and ethical compliance.

- Identify and Mitigate Risks: Understand the risks associated with crowdsourced data and how to mitigate them.

- Career Readiness: Be prepared for careers in data annotation by understanding the industry requirements, ethical standards, and best practices.

# Module Overview:

| Module Name | Theory (Hours) | Practical (Hours) | Total (Hours) |
| --- | --- | --- | --- |
| Module 1: Introduction to Python | 6 | 12 | 18 |
| Module 2: Python: Advanced | 4 | 8 | 12 |
| Module 3: Artificial Intelligence C Data Science Foundational | 4 | 6 | 10 |
| Module 4: Introduction to Data Annotation | 6 | 6 | 12 |
| Module 5: Text Annotation | 3 | 5 | 8 |
| Module 6: Image Annotation | 3 | 5 | 8 |
| Module 7: Video Annotation | 3 | 5 | 8 |
| Module 8: Audio Annotation | 3 | 5 | 8 |
| Module 9: AI-Assisted Annotation and Emerging Trends | 3 | 5 | 8 |
| Module 10: Quality Control and Best Practices | 3 | 5 | 8 |
| Module 11: Practical Projects with Industry | 0 | 16 | 16 |
| Module 12: Soft Skills Training | 2 | 2 | 4 |
| Total | 40 | 80 | 120 |

# Module 1: Introduction to Python

  - Theory (6 Hours)

    - Understanding to set up the Python environment.

    - Learning about variables and different data types in Python.

    - Understanding conditional statements (if, else, elif) and learning about loops (for, while).

    - Understanding the concepts of functions and learning to define and call functions.

# Practical (12 Hours)

    - Learning to install Python and an IDE.

    - Understanding to write and execute simple python scripts such as "Hello, World!”

    - Learning to perform basic operations with variables and data types.

    - Learning to write programs using conditional statements and loops.

    - Learning to create and use functions in Python programs.

# Module 2: Python: Advanced

  - Theory (4 Hours)

    - Understanding the basics of file handling in Python.

    - Understanding python lists (creation, indexing, slicing, etc.) and dictionaries (creation, accessing, etc.), their properties, and uses.

    - Understanding the basics of Python libraries -NumPy, Matplotlib, and Pandas.

# Practical (8 Hours)

    - Learning to read from and write to files using Python.

    - Learning to perform operations with lists and dictionaries in Python.

    - Learning to perform basic operations using various Python libraries.

    - Developing and implementing a project, integrating various concepts learned.

# Module 3: Artificial Intelligence s Data Science Foundational (10 Hours)

  - Theory (4 Hours)

    - Introduction to Artificial Intelligence

      - Understanding the basic concepts and evolution of Artificial Intelligence

      - Understanding the key components of Artificial Intelligence- Machine Learning, Deep Learning, Computer Vision C Natural Language Processing NLP.

      - AI in Healthcare, Finance, Education C Entertainment- Use cases C applications

      - Introduction to Generative AI – tools and use cases.

    - Basic Data Science and Statistics

      - Introduction to Data Science Concepts

      - Learning to handle large C complex datasets

      - Learning	to	implement	data	preprocessing	techniques-	Cleaning, Normalization, Handling Missing Data on sample datasets.

      - Understanding statistical Concepts: Distributions, Variance, Data Sampling

    - Ethical Considerations in AI

      - Introduction to AI Ethics and Biasness in AI models

      - Understanding Privacy Concerns with the use of AI

      - Understanding safe and responsible use of AI

# Practical (6 Hours)

    - Demonstration of popular AI tools

    - Demonstration of AI use cases in Healthcare, Finance, Education C Entertainment.

    - Hand on experience on open source GenAI tools.

    - Introduction to low-code/no-code AI platforms.

    - Various test cases to use preprocessing techniques- data cleaning, normalization, and handling missing data.

# Module 4: Introduction to Data Annotation (12 Hours)

  - Theory (6 Hours)

    - Overview of Data Annotation- definition and scope of data annotation

    - Understanding the difference between supervised and unsupervised learning.

    - Learning about the importance and impact of data annotation on the business.

    - Understanding the use cases and applications of data annotation across various industry verticals.

    - Introduction to various data annotation methods and understanding major differences between them.

    - Overview of Text, image, video, and audio annotation.

    - Understanding to handle various datasets- large-scale, complex datasets with limited labeled data

# Practical (6 Hours)

    - Hand on experience on the features and functionalities of various open-source Data Annotation tools.

    - Techniques to prepare datasets for annotation and machine learning tasks.

    - Understanding to Identify, tag, and label distinct elements in huge data sets.

    - Hands-on practice with different data types- Text, Audio, Video, Image

    - Learning to optimize the annotation process by focusing on the most informative samples.

# Module 5: Text Annotation (8 Hours)

  - Theory (3 Hours)

    - Understanding Basics of Text Annotation- definition and common use cases

    - Understanding various tools used for Text Annotation

    - Learning about various methods to classify text and Annotation schemas

    - Techniques and applications of performing Named Entity Recognition (NER)

    - Learning to assign grammatical weighted categories to various words in a text format.

    - Understanding various methods of sentiment analysis

# Practical (5 Hours)

    - Demonstrate the difference between various annotation methods and techniques, based on the project requirements and datasets

    - Practical exercises using open-source text annotation tools.

# Module 6: Image Annotation (8 Hours)

  - Theory (3 Hours)

    - Understanding Basics of Image Annotation- definition and common use cases

    - Learning the concepts of Image Annotation- Image segmentation, object detection, Bounding box, pixel-based polygon annotation.

# Practical (5 Hours)

    - Demonstrate the difference between various annotation methods and techniques, based on the project requirements and datasets

    - Learning Various Techniques and tools used for Image Segmentation C Object detection.

    - Learning Various Techniques of drawing bounding box in deep learning.

    - Understanding to use precise pixel-based polygon annotation.

    - Practical exercises using open-source image annotation tools.

# Module 7: Video Annotation (8 Hours)

  - Theory (3 Hours)

    - Understanding Basics of Video Annotation- definition and common use cases

    - Learning about Object Tracking: Target initialization, appearance modeling, motion estimation, target positioning, Frame-by-Frame Annotation.

# Practical (5 Hours)

    - Practical exercises on various techniques for scale variations, annotating out-of-view objects, low resolution, occlusion object tracking C Multi object tracking.

    - Hands on practical experiment on open-source tools.

# Module 8: Audio Annotation (8 Hours)

  - Theory (3 Hours)

    - Understanding basics of Audio Annotation: Definition and importance.

    - Learning about various types of Audio Data: Signals C formats used in annotation.

    - Understanding various techniques in Speech-to-Text conversion, multi-Speaker diarization C Emotion Detection.

# Practical (5 Hours)

    - Practical exercises using open source audio annotation tools.

    - Hand on experience on various techniques in Speech-to-Text conversion, multi-Speaker diarization C Emotion Detection.

    - Demonstrate the difference between various annotation methods and techniques, based on the project requirements and dataset.

# Module G: AI-Assisted Annotation and Emerging Trends (8 Hours)

  - Theory (3 Hours)

    - Introduction to cutting-edge trends such as 3D annotation for autonomous vehicles, synthetic data generation

    - Understanding to use Augmented C virtual reality in annotation tasks.

    - Understanding to review pre-annotated data from various AI tools and refining the outputs.

# Practical (5 Hours)

    - Hand on practical exercises of using open source AI assisted tools.

    - Learning about various techniques for ensuring high-quality annotations using automated tools- text, Image, Video C Audio.

    - Learning the use of augmented and virtual reality in annotation tasks.

    - Practical learning to cutting edge annotation trends- 3D annotation

# Module 10: Quality Control and Best Practices (8 Hours)

  - Theory (3 Hours)

    - Understanding techniques for Identification and mitigation of various common errors in annotation.

    - Learning to use Best Practices and the Guidelines for effective annotation.

    - Understanding ethical considerations: Ethical guidelines and best practices in Data Annotation.

    - Understanding AI Ethics and Responsible Annotation Practices

    - Learning techniques for Data Privacy Regulations and data anonymization

# Practical (5 Hours)

    - Demonstrate the difference between various annotation methods and techniques, based on the project requirements and dataset.

    - Learning to implement quality assurance techniques on sample datasets.

    - Learning strategies for difficult or unclear annotation scenarios.

    - Learning to handle edge cases and ambiguity in data annotation.

# Module 11: Practical Projects with Industry (16 Hours)

  - Practical (16 Hours)

    - Working on real world Data annotation problems sourced from Industry partners.

    - Learning to apply learned skills and knowledge in real world scenario

    - Learning to collaborate and work as a team for common objectives.

    - Presenting the project findings to the peers and instructor and learning to incorporate constructive feedback.

# Module 12: Soft Skills Training (4 Hours)

  - Theory (2 Hours)

    - Learning to explore career paths in Data annotations.

    - Communication Skills

    - Problem-Solving Techniques

    - Teamwork and Collaboration

# Practical (2 Hours)

    - Role-playing	exercises	and	group	activities	to	enhance	teamwork	and communication.

# Tools, Equipment and Other Requirements

  - Labs equipped with the following:

    - PCs/Laptops

    - Chart paper and sketch pens

    - Internet with Wi-Fi (Min 2 Mbps dedicated)

# Tools and Programming Languages:

    - Open-source Annotation Software.

    - Open-Source Computer Vision Tools.

    - Open-source NLP Tools.

    - Documentation tools (Adobe, MS-Word).

    - Documentation tools such as Adobe and MS-Word

    - Whiteboard, markers, LCD projector, laptops.

# Assessment:

    - Continuous assessment through quizzes, peer reviews, and feedback sessions.

    - Final project presentation and evaluation.

***

Annexure- III

Workstation

| Parameter | Minimum Specification |
| --- | --- |
| Type | Modular Computer Workstation suitable for AI Lab |
| Quantity | 20 Nos. |
| Material | Pre-laminated Particle Board (PLPB) / HDHMR Board / BWR Grade Plywood with laminate finish |
| Board Thickness | Minimum 25 mm top and 18 mm side panels |
| Edge Banding | Minimum 2 mm PVC edge banding on exposed edges |
| Frame | Powder-coated MS steel frame made from minimum 40 × 40 mm square tube or equivalent |
| Finish | Scratch-resistant, moisture-resistant laminate |
| Dimensions | Minimum 1200 mm (W) × 600 mm (D) × 750 mm (H) |
| Load Capacity | Minimum 80 kg uniformly distributed |
| Keyboard Tray | Heavy-duty telescopic sliding keyboard tray (optional if compact keyboard is used on desktop) |
| CPU Mount | Under-table metallic CPU holder or side-mounted CPU compartment |
| Cable Management | Integrated cable management tray with grommet holes and concealed wiring provision |
| Foot Rest | PVC/Steel footrest wherever required |
| Levelling | Adjustable nylon levelling bushes |
| Colour | Maple/Teak/Grey or approved institutional finish |
| Warranty | Minimum 3 Years |

### Additional Requirements

- Rounded corners for user safety.

- Smooth finished edges.

- Anti-rust metallic components.

- Suitable for continuous institutional usage.

- Capable of accommodating a desktop, monitor, keyboard and mouse simultaneously.

- Space for future dual-monitor installation.

- Cable routing shall ensure no exposed wiring.

# Student Chair

| Parameter | Minimum Specification |
| --- | --- |
| Type | Ergonomic Mid-Back Computer Chair |
| Quantity | 20 Nos. |
| Frame | Injection moulded reinforced nylon or powder-coated steel |
| Seat Material | High-density moulded PU foam |
| Upholstery | Fabric or breathable mesh with high abrasion resistance |
| Backrest | Ergonomic medium back with lumbar support |
| Seat Size | Minimum 460 mm × 460 mm |
| Back Height | Minimum 500 mm |
| Seat Height | Adjustable from 420 mm to 520 mm |
| Height Adjustment | Gas lift (Class 3 or better) |
| Base | Five-legged heavy-duty nylon or metal base |
| Castors | Twin-wheel nylon castors suitable for tiled/vinyl flooring |
| Armrests | Fixed or adjustable PP armrests |
| Weight Capacity | Minimum 120 kg |
| Colour | Black/Grey |
| Warranty | Minimum 3 Years |

Air-condition

| Parameter | Minimum Specification |
| --- | --- |
| Type | High Wall Split Inverter Air Conditioner |
| Star Rating | Minimum 5 Star (BEE) or latest applicable highest energy efficiency rating |
| Refrigerant | R-32 or environmentally friendly refrigerant |
| Cooling Capacity | Minimum 2 Ton per unit or as per approved heat load calculation |
| Compressor | Twin Rotary/Rotary Inverter Compressor |
| Power Supply | 230V AC ±10%, 50 Hz |
| Indoor Noise Level | Maximum 45 dB(A) |
| Outdoor Unit | Suitable for high ambient temperature operation up to 52°C |
| Air Flow | High airflow suitable for computer laboratory |
| Air Filters | HD Filter with washable filter |
| Copper Condenser | 100% Copper Condenser Coil |
| Copper Interconnecting Pipes | Insulated copper tubing |
| Drain Pipe | UPVC drain piping with proper slope |
| Remote Controller | Wireless remote with wall-mounted holder |
| Display | Digital temperature display |
| Auto Restart | Required |
| Timer Function | Required |
| Self Diagnosis | Required |
| Sleep Mode | Required |
| Turbo Cooling | Required |

# Round Discussion Table

| Parameter | Minimum Specification |
| --- | --- |
| Type | Circular Discussion/Collaboration Table |
| Quantity | 1 No. per AI Lab |
| Seating Capacity | Minimum 4 Persons |
| Table Top Material | 25 mm thick Pre-Laminated Particle Board (PLPB) / HDHMR Board / BWR Grade Plywood with laminate finish |
| Edge Banding | Minimum 2 mm PVC edge banding on all exposed edges |
| Diameter | Minimum 1200 mm |
| Height | 740–760 mm |
| Base Frame | Powder-coated Mild Steel (MS) frame with minimum 40 mm × 40 mm square tube or equivalent |
| Surface Finish | Scratch-resistant, stain-resistant and moisture-resistant laminate |
| Colour | Maple / Teak / Grey or approved institutional finish |
| Load Capacity | Minimum 100 kg uniformly distributed |
| Stability | Anti-skid nylon levelling bushes with wobble-free construction |
| Cable Management | Central cable access port with concealed cable management provision (preferred) |
| Corners | Rounded and smooth finished edges for safety |
| Warranty | Minimum 3 Years |

# Discussion Chairs

| Parameter | Minimum Specification |
| --- | --- |
| Type | Ergonomic Visitor/Discussion Chair |
| Quantity | 4 Nos. per AI Lab |
| Frame | Powder-coated MS tubular frame or reinforced polypropylene frame |
| Seat Material | Injection-moulded polypropylene (PP) with cushioned PU foam seat or upholstered fabric seat |
| Backrest | Ergonomic medium-height back with breathable perforated or mesh design |
| Seat Width | Minimum 450 mm |
| Seat Depth | Minimum 430 mm |
| Seat Height | 430–460 mm |
| Upholstery | Fabric or premium leatherette (where cushioned) |
| Weight Capacity | Minimum 120 kg |
| Armrests | Fixed PP armrests (preferred) |
| Finish | Scratch-resistant and corrosion-resistant |
| Stackable | Preferred for easy storage |
| Colour | Black, Grey or approved institutional colour |
| Warranty | Minimum 3 Years |

## FORM -1

COVERING LETTER (ON BIDDERS LETTER HEAD)

[Location, Date]

### To

The Chief Executive Officer

Chhattisgarh Infotech Promotion Society,

State Data Center, Civil Lines Raipur, (C.G.) 492001

Sub: Request for Proposal for Empanelment of Agencies for Supply, Installation, Commissioning, Training, Operation and Maintenance of Artificial Intelligence labs at Govt. ITIs and other Institutions across Chhattisgarh.

Dear Sir,

I/We …………………………. (Name of the Bidder) hereby submit our Proposal in response to notice inviting RFP date ………. and RFP document no	and confirm that:

- With reference to your RFP document dated	, I/we, having examined the Bidding Documents

and understood their contents, hereby submit my/our Bid. The Bid is unconditional and unqualified.

- I/We acknowledge that the CHiPS will be relying on the information provided in the Bid and the documents accompanying the Bid for selection of the Bidder for the aforesaid project(s), and we certify that all information provided therein is true and correct; nothing has been omitted which renders such information misleading; and all documents accompanying the Bid are true copies of their respective originals.

- This statement is made for the express purpose of qualifying as a Bidder for the aforesaid Project.

- I/ We shall make available to the CHiPS any additional information it may find necessary or require to supplement or authenticate the Bid.

- I/ We acknowledge the right of the CHiPS to reject our Bid without assigning any reason or otherwise and hereby waive, to the fullest extent permitted by applicable law, our right to challenge the same on any account whatsoever.

- I/ We certify that in the last three years, we have neither failed to perform on any contract, as evidenced by imposition of a penalty by an arbitral or judicial authority or a judicial pronouncement or arbitration award, nor been expelled from any project or contract by any public authority nor have had any contract terminated by any public authority for breach on our part.

- I/ We declare that:

  - I/ We have examined and have no reservations to the Bidding Documents, including any Addendum issued by the CHiPS;

  - I/We do not have any Conflict of Interest in accordance with the RFP document;

  - I/We have not directly or indirectly or through an agent engaged or indulged in any corrupt practice, fraudulent practice, coercive practice, undesirable practice or restrictive practice, as defined in the RFP document, in respect of any tender or request for proposal issued by or any agreement entered into with the CHiPS or any other public sector enterprise or any government, Central or State; and

  - I/ We hereby certify that we have taken steps to ensure that in conformity with the provisions of the RFP, no person acting for us or on our behalf has engaged or will engage in any corrupt practice, fraudulent practice, coercive practice, undesirable practice or restrictive practice.

- I/We understand that the CHiPS may cancel the Bidding Process at any time and that the CHiPS is neither bound to accept any Bid that you may receive nor to invite the Bidders to Bid for the Project, without incurring any liability to the Bidders.

- I/ We agree and undertake to abide by all the terms and conditions of the RFP document.

- I/ We offer a Bid Security/EMD to the CHiPS in accordance with the RFP document.

- I/ We agree and understand that the Bid is subject to the provisions of the Bidding Documents. In no case, I/we shall have any claim or right of whatsoever nature if the Project is not awarded to me/us or our Bid is not opened or rejected.

- I/ We certified that the period of validity of Proposal is till the end of the Contract Agreement period and I/We are quoting for all the services mentioned in the Scope of Work of the RFP.

- CHiPS, may contact the following person for further information regarding this Proposal:

Name and full address of office, Contact No., Email ID, Company Name

In witness thereof, I/we submit this Bid under and in accordance with the terms of the RFP document

Yours sincerely,

Authorized Signatory with Date and Seal:

### Name and Designation:

### Address of the Bidder:

### FORM-2

Bidder’s Organisation (General Details)

| SL No | Description | Full Details |
| --- | --- | --- |
| 1 | Name of the Bidder |  |
| 2 | Address for communication: Tel: E-mail ID: |  |
| 3 | Name of the authorized person signing & submitting the bid on behalf of the Bidder: Mobile No.: Email id: |  |
| 4 | Registration / Incorporation Details Registration No: Date & Year. : |  |
| 5 | Local office in Raipur If Yes, please furnish contact details | Yes / No |
| 6 | Bid Processing Fee Details Amount: |  |
| 7 | EMD Details Amount: |  |
| 8 | PAN Number |  |
| 9 | Goods and Services Tax Identification Number (GSTIN) |  |
| 10 | Willing to carry out the assignment as per the scope of work of RFP | YES |
| 11 | Accept all the terms and conditions as specified in the RFP | YES |

Authorized Signatory with Date and Seal:

Name and Designation:

### Address of the Bidder:

FORM-3

POWER OF ATTORNEY

### (Notarized copy on Rs. 100 Non-Judicial Stamp Paper)

(Required only if the Signatory is not directly authorized by the Company Board/Governing Body, or Partners. Otherwise, the Board Resolution/Partners Resolution would suffice)

Known all men by these presents, we……………………………………………. (name of the firm and address of the registered office) do hereby irrevocably constitute, nominate, appoint and authorize Mr./ Ms. (name), …………………… son/daughter/wife of	and presently residing at …………………., who is presently employed with us and holding the position of	, as

our true and lawful attorney (hereinafter referred to as the “Attorney”) to do in our name and on our behalf, all such acts, deeds and things as are necessary or required in connection with or incidental to submission of our tender against the Bid document no. [•] dated [•] published by CHiPS for the “Procurement of Goods – [•]”, including but not limited to signing and submission of all applications, bids and other documents and writings,

AND we hereby agree to ratify and confirm and do hereby ratify and confirm all acts, deeds and things done or caused to be done by our said Attorney pursuant to and in exercise of the powers conferred by this Power of Attorney and that all acts, deeds and things done by our said Attorney in exercise of the powers hereby conferred shall and shall always be deemed to have been done by us.

IN WITNESS WHEREOF WE…	, THE ABOVE-NAMED PRINCIPAL HAVE EXECUTED

THIS POWER OF ATTORNEY ON THIS ……… DAY OF	20[•].

For Witnesses

………………………………………………………………….. (Signature, name, designation and address)

1.

2.

Accepted

(Signature)

(Name, Title and Address of the Attorney)

Encl: Board resolution for Authorized signatory

## FORM - 4

(BIDDER’S PAST EXPERIENCE DETAILS)

### (List of orders/assignments only of similar nature)

| Sl. No. | Name of Buyer/Client, Address with Telephone No, e-mail, Contact Person, Mobile No. | Name of Project | Nature of Project/Goods/ Services and Brief of Project | Project Start Date and End Date | Project Cost/ Contract Value (In Rs.) | Status (Complete/ In Progress/ Delay) |
| --- | --- | --- | --- | --- | --- | --- |
| A | B | C | D | E | F | G |
| 1 |  |  |  |  |  |  |
| 2 |  |  |  |  |  |  |
| 3 |  |  |  |  |  |  |
| 4 |  |  |  |  |  |  |
| 5 |  |  |  |  |  |  |

#### Note: Information not conforming to the above format will be treated as non-responsive. The bidder must enlist their relevant experience for technical marking purpose. Copies of the Work order / Contract Document / Completion Certificate from the previous Clients need to be furnished along with the above information.

Authorized Signatory with Date and Seal:

Name and Designation:

Address of the Bidder:

## FORM - 5

### Affidavit for not being blacklisted

<< An affidavit on a non-judicial stamp paper of INR 100/- by Company Secretary/ Authorized Representative and Signatory of the Applicant with his/her dated Sign and duly notarized >>

## AFFIDAVIT

### (to be executed on INR 100 non-judicial stamp paper and to be duly notarized)

Date:

Sub: Tender No.

In response to the Tender Document above stated, I/We hereby declare and solemnly swear that our Company/ firm 	 is not banned/blacklisted as on date by any competent court of Law, forum or any State Government or Central Government or their agencies or by any statutory entities or any PSUs.

AND, if at any stage the declaration/statement on oath is found to be false in part or otherwise, then without prejudice to any other action that may be taken, I/We, hereby agree to be treated as a disqualified Bidder for the ongoing Contract.

In addition to the disqualification our concern/entity may be banned/blacklisted.

AND, that I/We, shall have no right whatsoever, to claim for consideration of my/our bid at any stage and the money deposited in the form of EMD shall be liable for forfeiture in full, and the tender, if any to the extent accepted, may be cancelled.

Signature of the Deponent

(Authorized signatory of the Bidder with Seal)

Date:

Place:

FORM-6

Technical Compliance Sheet

(To be submitted on Bidder’s Letterhead)

| Sl. No. | Product Name (As mentioned in ToR) | Technical Specifications (As per ToR) | Compliance (Yes/No) | If No, Reasons of deviations | Remarks (Additional features, if any) |
| --- | --- | --- | --- | --- | --- |

### Note:

The Technical compliance sheet shall provide a detailed list of identified requirements and specifications as mentioned in the ToR The bidder should indicate against the requirement in the compliance column to indicate the extent to which their proposals comply with the requirements. Bidder should also fill the details of proposed hardware and provide the necessary information.

The offered product within the scope of this RFP may have some features not contained in the ToR. Bidder may provide these details separately. These will not be part of above evaluation criteria.

Authorized Signatory with Date and Seal:

Name and Designation:

Address of the Bidder:

FORM –7

# Declaration regarding “Restrictions on procurement from a Bidder of a country which shares a land border with India”

(To be submitted on Bidder’s Letter Head)

To,

The Chief Executive Officer

Chhattisgarh Infotech Promotion Society,

State Data Center, Civil Lines Raipur, (C.G.) 492001

Dear Sir,

In reference to bid submitted by M/s 		against CHiPS Tender NIT Number: 	, I/We have read the restrictions on procurement from a bidder of a country which shares a land border with India and on sub-contracting to contractors from such countries.

I/We certify that M/s	(name of Bidder) is not from such a country and will not sub-contract any work to a contractor from such countries unless such contractor is registered with the Competent Authority. I also certify that M/s. 		will not offer any products/services of entity from such countries unless such entity is registered with the Competent Authority.

I/We certify that we/our Collaborator/Tie-Up Partners are/is not from such a country or, if from such a country, have/has been registered with the Competent Authority and we will not sub-contract any work to a contractor from such countries unless such contractor is registered with the Competent Authority.

We hereby certify that we fulfill all requirements in this regard and are eligible to be considered.

Authorized Signatory with Date and Seal:

Name and Designation:

Address of the Bidder:

## FIN-1

## COVERING LETTER

[Location, Date ]

To

The Chief Executive Officer

Chhattisgarh Infotech Promotion Society,

State Data Center, Civil Lines Raipur, (C.G.) 492001

Sub: Request for Proposal for Empanelment of Agencies for Supply, Installation, Commissioning, Training, Operation and Maintenance of Artificial Intelligence labs at Govt. ITIs and other Institutions across Chhattisgarh.

Sir,

I, the undersigned, offer to provide the Goods/Services for [Insert title of assignment] in accordance with your RFP No.	, Dated: 	. Our Financial Bid is for the sum of [Insert amount(s) in words and figures*]. This amount is inclusive of all the applicable taxes as per GST Act.

I do hereby undertake that, in the event of acceptance of our bid, the supply/services shall be provided with respect to the terms and conditions as stipulated in the RFP document. Equipment wise cost as per format (Annexure) given in the RFP documents are mentioned below:

| S.No. | Item | Unit Cost (INR) | No. of Students | Total (INR) | Tax (INR) | Gran Total (INR) |
| --- | --- | --- | --- | --- | --- | --- |
|  |  | A | C | C=(A*B) | D | E=C+D |
| 1 | Per student training cost per course |  | 180 |  |  |  |
| Total in words |  |  |  |  |  |  |

Note- Per student cost includes all the charges for Supply, Installation, Commissioning, Training, Operation and Maintenance of One (1) Artificial Intelligence lab for 3 years. Financial bid shall be evaluated on Total Cost of Ownership (TCO) basis considering the all-inclusive per student cost for 180 students over 3 years.

Authorized Signatory with Date and Seal:

### Name and Designation:

### Address of the Bidder:

FIN-2

BOQ-

## Bidder need to quote item wise rate for the below mentioned line items

## Note- The rates quoted are not for financial evaluation, any additional item shall be procured as per the below rates

| CATEGORY | USAGE | DESCRIPTION/SPECIFICATIONS | QTY | Unit Rate | Tax |
| --- | --- | --- | --- | --- | --- |
| Learning Zone | For Students to access and try program content in Lab Environment | 12th Generation Intel® CoreTMm 15-12500T with Intel vPro® Enterprise 8 GB DDR4- 3200 MHz RAM (1x 8) GB ‘ 512 GB PCleR NVMeTM M.2 SSD ; Intel® UHD; Graphics 770 Windows 11 Professional | 18 Nos. |  |  |
| Deep Learning & Inferencing Corner | Workstation for students to perform training and inferencing of deep learning models | 13th Generation Intel® CoreTM 17-13700K (30MB Cache), 16 Core (8+8), 3.40GHz to 5.40GHz (125W))TDP 32GB 2x16GB DDR5 UD , NECC, V2 Nvidia GeForce RTX3070 8GB 2TB PCle NVMe Class 40 M.2 SSD Windows 11 Pro, English | 2 Nos |  |  |
| Hardware Kit |  | Jetson Nano with Camera, Wifi dongle and SD Card and other Accessories | 5 Sets |  |  |
| Networking |  | Networking equipment like switch, CAT 6 Cable, rack, 9U Jack panel, 1 UPS, IO points+ Supply, Installation, commissioning and testing charges etc. | 1 Set |  |  |
| Audio Equipment |  | Audio visual equipment Projector with mount, amplifier, speaker, wireless mic | 1 Set |  |  |
| Printer |  | Laser | 1 No. |  |  |
| Consumables |  | Pen Drive, SD Card, Removables etc. | 1 Set |  |  |
| Software (with Perpetual License) |  | Python Anaconda Distribution Intel® Distribution for Python, OpenVINOTMm Toolkit, OneAPI, Intel® EMA, etc. Al Libraries and Frameworks: TensorFlow, PyTorch, Keras, scikit- learn, CUDA Toolkit for building and training models. Orange Data Mining (Free Version) Tableau (Free version) | 20 Users |  |  |
| Office Automation |  |  | 20 |  |  |
| AI Trainer (One for 36 months) for training |  |  | 1 |  |  |
| Lab Manpower (One for 36 months) for hand-holding |  |  | 1 |  |  |

Non-IT Requirements:

| CATEGORY | DESCRIPTION/SPECIFICATIONS | QTY | Unit Rate | Tax |
| --- | --- | --- | --- | --- |
| Furniture – Workstations and Chair | As per Annexure- III | 20 sets |  |  |
| AC | As per Annexure- III | 2 |  |  |
| Minor Civil Work | Whitewashing, Lights, Signage, Civil works | Lumpsum |  |  |
| Round Table and 4 chairs for collaborative zone | As per Annexure- III | Round Table-1 and Chairs-4 |  |  |