## Slide 1: Chhattisgarh AI Mission Implementation Roadmap
1 July 2026

## Slide 2: Implementation Roadmap Strategy
Phase I (Months 1–3)
Phase II (Months 4–6)
Phase III (Months 7–9):
Phase IV (Months 10–12
Mobilization & Use Case Discovery
Pilot Design & Ecosystem Activation
Pilot Implementation
Scale-up & Sustainability
Phase Wise Implementation Plan
Priority Wise PMU Support Activities and Deliverables
AI Talent and Institutional Capacity
AI Innovation & Startup Ecosystem
AI Awareness, Outreach & Ecosystem Engagement
Secure & Responsible AI
Strengthening AI-Enabled Governance

## Slide 3: Phase I (Months 1–3): Mobilisation & Use Case Discovery
Workstream | Activities | Deliverable
AI Use Cases | Preparing a preliminary list of AI Use Cases by reviewing AI interventions and best practices adopted by other states | List of AI Use Cases
 | Consultation/Workshops with Departments to Identify, refine and prioritize areas that need AI Interventions in the state and in govt. departments | Report on Need Assessment of AI in Govt Departments
 | Customize list of AI Use Cases to align with priorities of Chhattisgarh AI Mission | AI Use Case Compendium for Chhattisgarh
Access to GPUs | Identify the IndiaAI Mission's AI compute ecosystem, including eligibility criteria, minimum GPU/compute requirements, allocation framework and best practices adopted by other states, to determine the minimum viable compute requirement for Chhattisgarh. | AI Compute Requirement Assessment & Recommendation Report
 | Engage with the IndiaAI Mission to discuss the State's compute requirements, facilitate revisions to the GPU proposal (if required), and support the State in securing AI compute resources. | GPU Proposal Support Note
CoE Operationalisation | Benchmark AI Centres of Excellence across India and globally | List of activities for CoEs
 | Identify thematic focus areas for each CoE based on partner expertise | 
AI Labs | Examine best practices in AI skilling initiatives across other states and national programmes to assess curriculum, delivery mechanisms and partnership models foe AI Labs | AI Labs Benchmarking Report and Curriculum Framework
 | Identify academic institutions, industry experts, technology companies and training partners for programmes through AI Labs. | AI Labs Partnership and Engagement Plan
Partnerships | Initiate engagement with technology partners, academia and startups | -

## Slide 4: Phase II (Months 4–6): Pilot Design & Ecosystem Activation
Workstream | Activities | Key Deliverables
Centre of Excellence (CoEs) | Operationalise the Centres of Excellence (CoEs) by supporting IIIT Naya Raipur and NIT Raipur in defining focus areas, developing annual activity plans and initiating collaborative programmes. | CoE Operational Framework; Annual Activity Plans
AI Data Labs | Launch AI Labs by finalising implementation models, curriculum frameworks, infrastructure requirements and engaging academic institutions, industry experts and technology partners for AI skilling programmes. | AI Data Lab Implementation Framework; Lab Design & Infrastructure Guidelines; Curriculum & Training Framework; Institution & Partner Empanelment Report
AI Capacity Building | Roll out government AI skilling programmes by identifying training needs, designing learning frameworks and facilitating capacity-building initiatives for government officials and other stakeholders. | Training Needs Assessment Report; AI Skilling Plan; Capacity Building Progress Report/KPIs for Dashboard
AI Innovation Challenge | Launch the AI Innovation Challenge to crowdsource innovative AI solutions from startups, academia and students for priority government use cases and societal challenges. | Challenge Design Document,; Problem Statement Repository; Evaluation & Selection Framework
Startup Ecosystem Development | Initiate startup incubation and ecosystem development activities by engaging startups, incubators, investors, academic institutions and industry partners to foster AI innovation and entrepreneurship. | Startup Ecosystem Strategy; Incubation & Mentorship Framework
AI Use-case Identification | Identify and select 10–15 high-impact AI pilot projects in consultation with government departments, based on feasibility, strategic priorities and potential public value, for implementation in the subsequent phase. | Department-wise AI Use-case Assessment Report; AI Pilot Prioritisation Matrix; Pilot Project Concept Notes; Phase-II Implementation Pipeline

## Slide 5: Phase III (Months 7–9): Pilot Implementation
Workstream | Activities | Key Deliverables
Departmental AI Pilot Implementation Support | Implement departmental AI pilots by coordinating with implementing departments, Centres of Excellence, technology partners and other stakeholders to facilitate the development, testing and deployment of priority AI use cases. | AI Pilot Implementation Plans; Indicators for Pilot Deployment Dashboard
Capacity Building & Knowledge Support | Undertake continuous capacity building through workshops, training programmes and knowledge-sharing sessions for government officials, AI Labs, Centres of Excellence and other ecosystem stakeholders. | Capacity Building Calendar; Knowledge Repository and Learning Resources
Innovation Challenges & Hackathons | Organise AI innovation challenges and hackathons to encourage participation from startups, students, researchers and innovators in developing AI solutions for identified government use cases. | Hackathon & Innovation Challenge Rollout Strategy; Prototype Showcase Compendium; AI Solution Pipeline for Government Adoption
Startup Mentoring & Ecosystem Development | Facilitate startup mentoring and ecosystem engagement by connecting startups with academic institutions, industry experts, investors and government departments to support pilot development and innovation. | Startup Mentorship Programme Framework; Startup Engagement and Investor Connect Reports
Programme Monitoring & Documentation | Monitor and document implementation progress by tracking milestones, maintaining progress reports, documenting key achievements, challenges and lessons learnt, and preparing periodic status reports. | KPIs for Programme Monitoring Dashboard; Monthly & Quarterly Progress Reports; Lessons Learned and Best Practices Compendium
Mid-term Review & Course Correction | Conduct a mid-term implementation review to assess progress against planned activities, identify implementation gaps and recommend realignment or reprioritisation of activities, where required. | Mid-term Review Report; Gap Analysis & Corrective Action Plan; Revised Implementation Roadmap; Recommendations for Phase III Implementation

## Slide 6
Phase IV (Months 10–12): Scale-up & Sustainability
Workstream | Activities | Key Deliverables
AI Pilot Evaluation & Validation | Evaluate AI pilot projects to assess outcomes, implementation challenges and readiness for wider adoption. | AI Pilot Evaluation Reports; Pilot Performance & Outcome Assessment
Scale-up Planning & Departmental Adoption | Scale successful AI solutions by identifying high-impact pilots for expansion across departments and supporting implementation planning. | AI Scale-up Strategy & Implementation Plan; Department-wise Roll-out Roadmaps; Scale-up Prioritisation Matrix
Year-2 Strategic Planning | Prepare the Year-2 implementation roadmap based on lessons learnt, emerging priorities and future mission objectives. | Year-2 AI Mission Implementation Roadmap; Strategic Priority & Resource Planning Report
Mission Reporting & Performance Review | Develop the Annual AI Mission Report highlighting key achievements, milestones, partnerships and implementation progress. | Annual AI Mission Report; Mission Performance Dashboard; Partnership & Milestone Report
Knowledge Management & Documentation | Establish a knowledge repository to capture project documentation, case studies, best practices and reusable resources developed during the Mission. | AI Mission Knowledge Repository; Best Practices & Case Study Compendium; Standard Templates & Toolkits Repository
Impact Assessment & Future Strategy | Conduct an impact assessment to evaluate the Mission's progress against defined KPIs and recommend strategic interventions for the next phase. | Mission Impact Assessment Report; KPI for Achievement & Outcome Evaluation; Strategic Recommendations Report

## Slide 7: AI Talent and Institutional Capacity– PMU Support and Deliverables

## Slide 8: AI Talent and Institutional Capacity
Workstream | Activities | Deliverable
School AI Capacity Building | Conduct baseline assessment of AI readiness of School Education Department and government schools | Assessment Report; Annual Implementation Plan and rollout strategy
 | Stakeholder consultations to identify pilot districts and schools based on predefined criteria | District-wise Rollout Plan
 | Identify and facilitate empanelment of training partners | RFP Preparation
 | Support preparation of teacher capacity-building framework | Devise Teacher Training Strategy and Training Calendar
 | Develop monitoring indicators and reporting formats | Monitoring Framework, KPIs and Dashboard Templates
Higher Education | Assess AI readiness of universities and colleges | Assessment Report, Annual Implementation Plan and rollout strategy
 | Stakeholder consultations to identify priority institutions for phased rollout | Institutional Prioritization Report; AI Implementation Framework
 | Assist departments in designing AI certification ecosystem | Certification Framework
 | Develop student innovation grant operational guidelines | Student Innovation Grant Guidelines
 | Support planning of hackathons and innovation challenges | Annual Innovation Calendar

## Slide 9: AI Talent and Institutional Capacity
Workstream | Activities | Deliverable
ITIs & Polytechnics | Conduct demand assessment for AI-enabled industrial skills | Skill Gap Assessment Report
 | Identify trades suitable for AI integration | AI Trade Prioritization Report
 | Develop instructor training roadmap | ToT Roadmap
Faculty & Trainer Development | Conduct Training Needs Assessment and prepare faculty development strategy | Assessment report and capacity building rollout strategy
 | Support empanelment of master trainers | RFP Preparation
 | Prepare training calendar | Annual Training Calendar

## Slide 10: AI Innovation & Startup Ecosystem – PMU Support and Deliverables

## Slide 11: AI Innovation & Startup Ecosystem
Workstream | Activities | Deliverable
AI Data Labs | Support preparation of technical specifications | Devise Technical Design & Infrastructure Specifications
 | Prepare implementation roadmap for phased rollout | Data Lab Rollout Plan
 | Develop monitoring indicators | KPIs for Performance Monitoring Dashboard
AI Centres of Excellence (CoEs) | Identify sectoral priorities and CoE focus areas | CoE Strategy
 | Support preparation of DPRs | Detailed Project Reports
 | Facilitate partnerships with academia and industry | Partnership & Collaboration Plan
 | Develop research and innovation roadmap | Five-Year Research Roadmap
 | Prepare operational guidelines | CoE Operations Manual
 | Monitor institutional performance | KPIs for CoE Performance Dashboard

## Slide 12: AI Innovation & Startup Ecosystem
Workstream | Activities | Deliverable
Startup Incubation & Acceleration | Develop startup lifecycle support model | Startup Rollout Plan
 | Prepare startup selection and evaluation criteria | Selection & Evaluation Guidelines
 | Develop mentor onboarding framework | Mentor & Expert Network Framework
 | Design startup monitoring indicators | Startup KPI Framework
Challenge-Based Innovation Programmes | Support departments in identifying AI use cases | Department-wise AI Problem Statement Repository
 | Prepare challenge programme framework | Innovation Challenge Programme Plan
 | Develop evaluation criteria | Technical Evaluation Framework

## Slide 13: AI Innovation & Startup Ecosystem
Workstream | Activities | Deliverable
State AI Sandbox | Develop Sandbox operating model | AI Sandbox Framework
 | Prepare technical testing protocols | Sandbox Testing Protocols
 | Develop privacy, security and compliance checklist | Responsible AI Compliance Framework
 | Prepare pilot evaluation methodology | Pilot Evaluation Framework
 | Develop onboarding process | Sandbox User Manual
 | Monitor pilot performance | Sandbox Performance Dashboard
Innovation Grants & Incentive Support | Prepare eligibility and evaluation criteria | Grant Operational Guidelines
 | Support proposal evaluation | Technical Evaluation Reports
Applied Research & Academic Collaboration | Identify priority research themes | State AI Research Agenda
 | Facilitate collaboration among academia, industry and government | Collaboration Strategy
 | Support research proposal evaluation | Research Review Reports

## Slide 14: AI Awareness, Outreach & Ecosystem Engagement– PMU Support and Deliverables

## Slide 15: AI Awareness, Outreach & Ecosystem
Workstream | Activities | Deliverable
Department of Public Relations | Support development of communication campaigns and IEC content strategy | IEC Content & Communication Framework
 | Develop standardized outreach templates and communication toolkits | AI Mission Outreach Toolkit
 | Support preparation of district-level communication plans | District Outreach Communication Plans
District Administration | Support preparation of district-level communication plans | District Outreach Communication Plans
 | Monitor outreach campaigns and analyse coverage | Media Monitoring & Outreach Analytics Report
AI Awareness Campaigns | Conduct stakeholder mapping for awareness campaigns | Stakeholder Mapping Report
 | Develop AI awareness campaign strategy for different target groups | AI Awareness Strategy
 | Prepare multilingual IEC materials and outreach content framework | IEC Content Repository
Knowledge Management | Develop standardized case study templates | Case Study Documentation Framework
 | Prepare annual knowledge compendium | AI Mission Knowledge Compendium

## Slide 16: AI Awareness, Outreach & Ecosystem
Workstream | Activities | Deliverable
AI Knowledge Series, Workshops & Public Lectures | Prepare annual calendar for knowledge events | AI Knowledge Series Calendar
 | Identify knowledge partners, speakers and institutions | Expert & Knowledge Partner Database
 | Develop themes aligned with Mission priorities | Annual Thematic Framework
Conferences, Summits & Outreach Events | Facilitate partnerships with academic institutions, industry and government | Partnership & Sponsorship Plan
 | Support agenda design and speaker engagement | Conference Agenda & Speaker Briefs
Community & Inclusive Outreach | Develop inclusive outreach strategy for tribal communities, women and underserved groups | Inclusive Outreach Strategy
 | Prepare localized communication framework | Multilingual IEC Framework
 | Support stakeholder mapping of SHGs, CSOs and community institutions | Community Stakeholder Database
 | Monitor outreach coverage across districts | Inclusion Monitoring Dashboard

## Slide 17: Secure & Responsible AI– PMU Support and Deliverables

## Slide 18: Secure & Responsible AI
Workstream | Activities | Deliverable
Alignment with Government of India Frameworks | Review national laws, policies and advisories relevant to AI | Regulatory Landscape Assessment Report
 | Develop guidance notes for departments on implementation | Department Advisory Notes
Data Governance & Privacy | Develop model data governance templates and protocols | Data Governance Toolkit
 | Support departments in adoption of data governance practices | Departmental Data Governance Advisory Reports
Security-by-Design | Develop baseline security recommendations for AI projects | Security-by-Design Guidance Document
 | Prepare standard security checklist for AI solution design | AI Security Checklist
Departmental Trusted AI Readiness | Conduct departmental awareness sessions on Responsible AI | Department Orientation Materials
 | Assist departments in applying Responsible AI templates and checklists | Responsible AI Compliance Toolkit
 | Develop training modules on Responsible AI, privacy and AI governance | Training Modules & Learning Materials
 | Develop awareness manuals and guidance documents | User Manuals & Guidance Notes
Standardization & Toolkits | Develop AI risk assessment templates | AI Risk Assessment Template
 | Prepare vendor due diligence formats | Vendor Due Diligence Framework

## Slide 19: Strengthening AI-Enabled Governance– PMU Support and Deliverables

## Slide 20: Strengthening AI-Enabled Governance
Workstream | Activities | Deliverable
Department AI Readiness, Use-case Identification and AI Adoption Roadmaps | Identify governance pain points, process inefficiencies and citizen service gaps | Department Diagnostic & Opportunity Assessment Report
 | Facilitate AI use-case discovery workshops with departments | Department-wise AI Use-case Repository
 | Benchmark comparable AI implementations from other governments | Best Practice & Benchmarking Report
 | Prioritize AI use-cases based on feasibility and public value | AI Use-case Prioritization Matrix
 | Recommend phased implementation and scale-up pathways | AI Implementation Roadmap
Government Generative AI Guidance | Develop guidance for government use of Generative AI | Government Generative AI Usage Guidelines
 | Prepare model prompts, disclosure guidance and review protocols | Generative AI Operational Toolkit

## Slide 21: Strengthening AI-Enabled Governance
Workstream | Activities | Deliverable
AI Application Repository & Technical Coordination | Support Mission Directorate in documenting AI applications across departments | State AI Application Repository
 | Develop AI use-case catalogue with implementation status | AI Use-case Catalogue
 | Track implementation progress of departmental AI initiatives | AI Project Tracking Dashboard
Capacity Building for AI-enabled Governance | Conduct departmental consultations for AI adoption | Consultation Reports
 | Support integration planning with existing digital governance systems | Integration Advisory Manual/Report
 | Prepare orientation modules for AI adoption | Training Modules, AI Governance Handbook